## Roadmap
Rovvy Travel Unit — Flights Scrum Roadmap
Six proposed two-week sprints · dates and working hours are editable planning assumptions
Sprint | Sprint Context | Goal Count | Feature Goals | Start | End | Planned Hours | Current Completion | Expected Result | Review Status
Sprint 1: Redirect-only product alignment | Rovvy is an aggregator, not the merchant of record. This sprint removes every public path and message that could make users believe Rovvy sells, issues, changes, cancels, or supports flight tickets. | 7 | G1.1 Make redirect-only behavior the single public Flights path ¦ G1.2 Disable internal checkout entry points and booking CTAs ¦ G1.3 Add consistent development-preview disclosure ¦ G1.4 Allow guest comparison and provider handoff ¦ G1.5 Replace booking language with comparison language ¦ G1.6 Add provider-owned payment and support disclosure ¦ G1.7 Regression tests for prohibited checkout paths and copy | 2026-08-24 12:00 | 2026-09-04 12:00 | 72 | 100% | Public Flights journey is redirect-only; test inventory is non-bookable; product language is consistent. | Technical Complete — PO Review Pending
Sprint 2: Provider governance and safe handoff | Provider names and prices are trustworthy only when access is authorized and the handoff is safe. This sprint creates the lifecycle, authorization, environment, and redirect controls required before any seller is actionable. | 7 | G2.1 Enforce provider activation gate ¦ G2.2 Separate registered, configured, enabled and actionable states ¦ G2.3 Block non-actionable seller prices from selection ¦ G2.4 Add authorization type and terms-review metadata ¦ G2.5 Separate test and live seller presentation ¦ G2.6 Implement redirect-domain allowlist and validation ¦ G2.7 Provider failure and partial-result security tests | 2026-09-07 12:00 | 2026-09-18 12:00 | 76 | 0% | Provider activation is governed; redirects are HTTPS, allowlisted and safe; failures remain transparent. | Pending
Sprint 3: Aggregation correctness | A provider may return several timings, and several providers may return the same itinerary. This sprint preserves distinct journeys while grouping only exact itinerary matches into comparable seller options. | 7 | G3.1 Expand itinerary fingerprint coverage ¦ G3.2 Verify exact-match itinerary grouping ¦ G3.3 Prevent near-match itinerary collisions ¦ G3.4 Normalize currencies while preserving source values ¦ G3.5 Define transparent seller ordering ¦ G3.6 Add sanitized provider contract fixtures ¦ G3.7 Expired and duplicate offer regression suite | 2026-09-21 12:00 | 2026-10-02 12:00 | 80 | 0% | Exact matching flights group into seller options; distinct or expired journeys remain separate. | Pending
Sprint 4: Results experience and group usefulness | The results page must help solo and group travelers make a decision quickly. This sprint improves hierarchy, explanations, accessibility, responsive behavior, sharing, and post-booking Trip Space usefulness. | 7 | G4.1 Add search freshness and provider coverage summary ¦ G4.2 Present itinerary with provider count and starting price ¦ G4.3 Keep materially weaker alternatives collapsed ¦ G4.4 Explain Rovvy recommendation reasons ¦ G4.5 Design confirmed-flight attachment to Trip Space ¦ G4.6 Accessibility and responsive visual regression ¦ G4.7 Usability review with solo and group scenarios | 2026-10-05 12:00 | 2026-10-16 12:00 | 78 | 0% | Compact accessible results clearly explain flight tradeoffs and support Trip Space planning. | Pending
Sprint 5: First authorized external source | Rovvy needs one lawful, provider-approved data source before presenting real offers. This sprint is deliberately limited to an adapter foundation and one authorized evaluation integration; named providers are not shown until permission and credentials exist. | 2 | G5.1 Complete the provider-neutral redirect adapter and authorization gate ¦ G5.2 Connect and verify one authorized evaluation provider | 2026-10-19 12:00 | 2026-10-30 12:00 | 80 | 0% | One authorized source returns real/test offers with an itinerary-specific external handoff. | Pending
Sprint 6: Release hardening and evidence package | The non-commercial preview must be stable enough for demonstrations and provider discussions. This sprint proves security, resilience, performance, disclosure quality, operational readiness, and release ownership. | 8 | G6.1 Create one release test command and CI quality gate ¦ G6.2 Complete redirect, credential, logging and error security review ¦ G6.3 Verify concurrent-provider performance ¦ G6.4 Prove empty, stale, expired, timeout and partial-result behavior ¦ G6.5 Prepare the product demonstration script ¦ G6.6 Prepare the provider architecture and evidence brief ¦ G6.7 Approve privacy, terms and development-preview disclosures ¦ G6.8 Complete Product Owner release and rollback decision | 2026-11-02 12:00 | 2026-11-13 12:00 | 70 | 0% | Rovvy demonstrates trustworthy comparison without internal booking, commissions or misleading data. | Pending
Overall planned window: August 24, 2026 – November 13, 2026. Standard working block: Monday–Friday, 9:00 AM–5:00 PM Central Time. Ceremony times are listed inside every sprint box.

## Sprint 1
Sprint 1 — Redirect-only product alignment
A user can search and compare flights without entering any Rovvy checkout flow.
Start Date | 2026-08-24 12:00 | End Date | 2026-09-04 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 72
EXPECTED SPRINT RESULT — Public Flights journey is redirect-only; test inventory is non-bookable; product language is consistent.
SPRINT CONTEXT
Rovvy is an aggregator, not the merchant of record. This sprint removes every public path and message that could make users believe Rovvy sells, issues, changes, cancels, or supports flight tickets.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G1.1 | Make redirect-only behavior the single public Flights path |  |  | Public comparison journey never enters Rovvy checkout |  |  |  | FL-001 | Complete
G1.2 | Disable internal checkout entry points and booking CTAs |  |  | No public link reaches travelers, extras, review or payment |  |  |  | FL-002 | Complete
G1.3 | Add consistent development-preview disclosure |  |  | Test status is visible before seller selection |  |  |  | FL-003 | Complete
G1.4 | Allow guest comparison and provider handoff |  |  | Authentication is not required to compare or redirect |  |  |  | FL-004 | Complete
G1.5 | Replace booking language with comparison language |  |  | All public copy uses Compare providers / Continue to provider |  |  |  | FL-041 | Complete
G1.6 | Add provider-owned payment and support disclosure |  |  | Responsibility is clear beside every future redirect |  |  |  | FL-044 | Complete
G1.7 | Regression tests for prohibited checkout paths and copy |  |  | Automated tests prevent aggregator/OTA regression |  |  |  | QA-101 | Complete
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-08-24 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-09-04 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-09-04 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-001 | Make redirect-only behavior the single public Flights path | Product + Frontend | 14 | 2026-08-24 12:00 | 2026-08-28 12:00 | Public comparison journey never enters Rovvy checkout | Complete | P0 | Public result actions are external_redirect only when a provider URL exists; missing links are unavailable.
FL-002 | Disable internal checkout entry points and booking CTAs | Frontend | 14 | 2026-08-24 12:00 | 2026-08-28 12:00 | No public link reaches travelers, extras, review or payment | Complete | P0 | Offer, checkout and booking route families render no protected content and redirect to /flights while product mode is disabled.
FL-003 | Add consistent development-preview disclosure | Product + Frontend | 8 | 2026-08-24 12:00 | 2026-08-28 12:00 | Test status is visible before seller selection | Complete | P0 | Test inventory is labeled before selection and states that no real booking will be created.
FL-004 | Allow guest comparison and provider handoff | Frontend | 10 | 2026-08-31 12:00 | 2026-09-04 12:00 | Authentication is not required to compare or redirect | Complete | P0 | Guests can search, compare and follow an eligible external seller link without authentication.
FL-041 | Replace booking language with comparison language | Product | 10 | 2026-08-31 12:00 | 2026-09-04 12:00 | All public copy uses Compare providers / Continue to provider | Complete | P0 | Reachable Flights UI uses comparison and provider-handoff language; historical checkout copy remains unreachable behind the guard.
FL-044 | Add provider-owned payment and support disclosure | Product + QA | 8 | 2026-08-31 12:00 | 2026-09-04 12:00 | Responsibility is clear beside every future redirect | Complete | P0 | Every seller option identifies seller responsibility for payment, ticketing, changes, cancellations, refunds and support.
QA-101 | Regression tests for prohibited checkout paths and copy | QA | 8 | 2026-08-31 12:00 | 2026-09-04 12:00 | Automated tests prevent aggregator/OTA regression | Complete | P0 | Verified: TypeScript 0 errors; Vitest 47 files/239 tests; focused backend 57 passed; full backend 872 passed, 4 skipped. Behavioral route-guard coverage remains a recommended hardening item.
SPRINT REVIEW BOX
Review Date | 2026-09-04 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Technical Complete | Completion | 100% | Reviewer | Product Owner
Actual Result | Verified August 25, 2026: the public Flights journey is redirect-only; missing provider links are unavailable; internal offer/checkout/booking UI is guarded; guest external handoff and seller responsibility disclosures are implemented. TypeScript passed, 239 frontend tests passed, 57 focused backend tests passed, and the full backend suite passed 872 with 4 skipped.
Decision / Follow-up | Technical result complete. Product Owner acceptance remains pending. Recommended follow-up: add behavioral component tests for router redirects, protected-child non-rendering and absence of booking requests; existing regression coverage is primarily source/static plus backend behavior.
CURRENT STATE AUDIT — WHAT ROVVY HAS DONE AND WHAT SPRINT 1 STILL REQUIRES
Goal | Implemented now |  |  | Remaining gap |  |  | Assessment | Evidence | Verified
G1.1 | Public results normalize only eligible external redirects; missing links are unavailable. |  |  | No remaining Sprint 1 implementation gap. |  |  | Complete | normalizer.py; results/page.tsx; FlightOptionsDrawer.tsx | 2026-08-25 2:35 AM CT
G1.2 | Disabled product-mode guards cover offer, checkout and booking route families and render no protected children. |  |  | Behavioral router-mock coverage is recommended hardening, not a public-path blocker. |  |  | Complete | flight-product-mode.ts; offer page; checkout/booking layouts | 2026-08-25 2:35 AM CT
G1.3 | Test/sandbox inventory is visibly labeled and non-bookable when no external link exists. |  |  | No remaining Sprint 1 implementation gap. |  |  | Complete | FlightTrustStrip.tsx; FlightOptionsDrawer.tsx | 2026-08-25 2:35 AM CT
G1.4 | Guest search, comparison and eligible external provider handoff require no sign-in. |  |  | Production handoff depends on future authorized provider links. |  |  | Complete | results/page.tsx; FlightOptionsDrawer.tsx | 2026-08-25 2:35 AM CT
G1.5 | Reachable Flights screens use View options, Compare providers and Continue to provider language. |  |  | Historical checkout copy remains dormant behind the disabled guard. |  |  | Complete | flights/page.tsx; results/page.tsx; route guards | 2026-08-25 2:35 AM CT
G1.6 | Seller responsibility for payment, ticketing, changes, cancellations, refunds and support appears beside each option. |  |  | No remaining Sprint 1 implementation gap. |  |  | Complete | FlightOptionsDrawer.tsx | 2026-08-25 2:35 AM CT
G1.7 | Regression suites prohibit public provider_checkout and verify unavailable fallbacks and disclosures. |  |  | Add behavioral route-guard tests during hardening for stronger assurance. |  |  | Complete | Vitest 239; focused pytest 57; full pytest 872 passed/4 skipped; tsc passed | 2026-08-25 2:35 AM CT
CURSOR DELIVERY PLAN — REQUIRED WORK FOR SPRINT 1
Step | Files / area |  |  | Required implementation |  |  | Acceptance evidence
1 | flight provider normalizer + results fallback |  |  | Map offers to external_redirect only when a validated redirect URL exists; otherwise use unavailable. Never create provider_checkout in the public result model. |  |  | Backend and frontend tests prove a missing redirect cannot become an internal checkout action.
2 | FlightOptionsDrawer.tsx |  |  | Remove login/auth restoration and internal /flights/offer links. Render external HTTPS handoff or a disabled test/unavailable state. |  |  | No getToken, authHref, providerCheckoutHref, Sign in to continue, or internal offer link remains.
3 | Flights offer/checkout/booking pages |  |  | Add one disabled product-mode guard so direct public navigation returns to /flights (or not-found) without touching environment files. |  |  | Direct URLs cannot show traveler, extras, review, payment, processing or confirmation UI.
4 | Public Flights copy |  |  | Use View options / Compare providers / Continue to provider consistently; add seller-owned payment, ticketing, changes, cancellations and support disclosure beside actions. |  |  | Static copy tests scan all public Flights entry points and prohibit Rovvy-booking language.
5 | Regression tests |  |  | Rewrite frontend and backend tests that currently expect provider_checkout; add route-guard, guest redirect, missing-link, test-disclosure and prohibited-copy coverage. |  |  | Focused suites pass with zero assertions preserving internal checkout behavior.
6 | Verification + records |  |  | Run focused frontend tests, relevant backend tests and TypeScript. Record exact results in this Sprint Review box and update the Feature/Test registries without inventing totals. |  |  | Commands, counts, failures and any carry-over are written into the workbook and project rule registries.
COPY-READY GPT / CURSOR PROMPT
TASK: Rovvy Flights — Complete Sprint 1: Redirect-only product alignment AUTHORITATIVE PROJECT: D:\group travel os READ FIRST: AGENTS.md, .cursorrules, GEMINI.md, CLAUDE.md, Scram Book\README.md, Scram Book\Travel Tab\Rovvy_Travel_Flights_Scrum_Plan.xlsx (Sprint 1), and Rovvy_Flights_Detailed_Product_Report.docx. OBJECTIVE Make the only public Flights journey: search → compare itineraries → view seller options → open the chosen authorized external provider. Rovvy must not collect traveler/payment data, create a flight order, or require sign-in merely to leave for a provider. Preserve existing brand and search/results UI unless a change is required for this boundary. REQUIRED CHANGES 1. In provider normalization and the results fallback, emit external_redirect only for a validated HTTPS redirect URL. When no redirect exists (including Duffel sandbox), emit unavailable—not provider_checkout. 2. In FlightOptionsDrawer.tsx remove getToken/authHref/login restoration, providerCheckoutHref, internal /flights/offer navigation, and all provider_checkout CTAs. Show an external link only when actionable; otherwise show a disabled Test offer / external link unavailable state. 3. Add a centralized, disabled internal-checkout product-mode guard. Direct public visits to /flights/offer/*, /flights/checkout/* and /flights/booking/* must redirect to /flights or render not-found while Sprint 1 is active. Do not edit any .env file. Historical booking code may remain unreachable for reference. 4. Standardize public copy: View options, Compare providers, Continue to provider. Beside every enabled redirect state: “You’ll complete payment and manage tickets, changes, cancellations, and support with [seller]. Rovvy does not issue or service tickets.” Never show Complete your booking, Pay & Book, Secure booking through Rovvy, or similar claims on a reachable public Flights screen. 5. Replace tests that currently expect provider_checkout, /flights/offer login restoration, or sign-in-to-continue. Add regression coverage for: guest comparison/redirect, missing redirect disabled, sandbox disclosure, expired offer disabled, internal route guard, prohibited copy, and external HTTPS handoff. 6. Do not invent Priceline, Expedia, MakeMyTrip, EaseMyTrip, Agoda, airline-direct, or other sellers. A provider appears only with authorized configured data and a real itinerary-specific redirect. Do not scrape providers. FILES TO INSPECT (not an automatic permission to rewrite unrelated code) frontend/components/travel/FlightOptionsDrawer.tsx; frontend/app/(dashboard)/flights/results/page.tsx; frontend/app/(dashboard)/flights/offer/[offerId]/; frontend/app/(dashboard)/flights/checkout/; frontend/app/(dashboard)/flights/booking/; frontend/lib/__tests__/flight-metasearch.test.ts; frontend/lib/__tests__/flight-amadeus-ui.test.ts; app/services/flight_providers/normalizer.py; tests/test_flight_metasearch.py. VERIFICATION Run the focused Flights frontend tests, relevant backend flight-metasearch tests, and npx tsc --noEmit. Report exact commands and results. Search reachable public Flights files for prohibited booking language and internal checkout links. Update GEMINI.md/.cursorrules registries only with verified totals. Update Sprint 1 in the Scram Book with actual evidence, completion percentage, carry-over, and review decision. DEFINITION OF DONE No public result or provider option can enter Rovvy checkout; no guest is asked to sign in to redirect; test offers without links are disabled and honest; provider responsibility is explicit; direct internal checkout URLs are blocked; regression tests prevent reversal.
SPRINT 1 TECHNICAL RESULT — Complete. Product Owner review and acceptance remain pending. Authorized live-provider onboarding is outside Sprint 1.
LATEST SPRINT 1 VERIFICATION — AUGUST 25, 2026 · 2:35 AM CT
Check | Command / Scope |  |  | Result |  |  | Impact on Sprint 1 | Status | Owner / Follow-up
Code re-audit | Normalizer, public results/drawer, product-mode guards and disclosures |  |  | Redirect-only public flow verified; missing links unavailable; internal route UI suppressed. |  |  | Sprint 1 technical requirements implemented. | Passed | Product Owner review
Frontend tests | Vitest full frontend suite |  |  | 47 files passed; 239 tests passed. |  |  | No frontend regression detected. | Passed | None
Backend focused tests | pytest: metasearch, Phase 2 connections, multi-provider aggregator |  |  | 57 passed; one dependency warning. |  |  | Focused flight behavior is green. | Passed | Monitor warning
Frontend types | tsc --noEmit |  |  | Passed with zero TypeScript errors. |  |  | Previous three compilation errors resolved. | Passed | None
Full backend / Sprint decision | pytest -q; Product Owner gate |  |  | 872 passed, 4 skipped, 41 warnings. Technical result complete. |  |  | Product Owner acceptance is not self-approved. | Awaiting PO | Product Owner

## Sprint 2
Sprint 2 — Provider governance and safe handoff
Only authorized, configured and actionable providers can appear as selectable sellers.
Start Date | 2026-09-07 12:00 | End Date | 2026-09-18 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 76
EXPECTED SPRINT RESULT — Provider activation is governed; redirects are HTTPS, allowlisted and safe; failures remain transparent.
SPRINT CONTEXT
Provider names and prices are trustworthy only when access is authorized and the handoff is safe. This sprint creates the lifecycle, authorization, environment, and redirect controls required before any seller is actionable.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G2.1 | Enforce provider activation gate |  |  | Only configured + enabled + authorized + actionable sellers appear |  |  |  | FL-010 | Pending
G2.2 | Separate registered, configured, enabled and actionable states |  |  | Provider directory accurately reports lifecycle state |  |  |  | FL-011 | Pending
G2.3 | Block non-actionable seller prices from selection |  |  | Unavailable sellers have no Continue action |  |  |  | FL-012 | Pending
G2.4 | Add authorization type and terms-review metadata |  |  | Every production provider has auditable authorization metadata |  |  |  | FL-013 | Pending
G2.5 | Separate test and live seller presentation |  |  | Sandbox results cannot visually impersonate live inventory |  |  |  | FL-045 | Pending
G2.6 | Implement redirect-domain allowlist and validation |  |  | Unknown, non-HTTPS and malformed redirects are blocked |  |  |  | FL-071 | Pending
G2.7 | Provider failure and partial-result security tests |  |  | One failed provider does not hide successful results |  |  |  | QA-201 | Pending
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-09-07 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-09-18 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-09-18 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-010 | Enforce provider activation gate | Backend | 14 | 2026-09-07 12:00 | 2026-09-11 12:00 | Only configured + enabled + authorized + actionable sellers appear | Not Started | P0
FL-011 | Separate registered, configured, enabled and actionable states | Backend | 10 | 2026-09-07 12:00 | 2026-09-11 12:00 | Provider directory accurately reports lifecycle state | Not Started | P0
FL-012 | Block non-actionable seller prices from selection | Backend + Frontend | 10 | 2026-09-07 12:00 | 2026-09-11 12:00 | Unavailable sellers have no Continue action | Not Started | P0
FL-013 | Add authorization type and terms-review metadata | Product + Backend | 10 | 2026-09-14 12:00 | 2026-09-18 12:00 | Every production provider has auditable authorization metadata | Not Started | P1
FL-045 | Separate test and live seller presentation | Frontend | 10 | 2026-09-14 12:00 | 2026-09-18 12:00 | Sandbox results cannot visually impersonate live inventory | Not Started | P0
FL-071 | Implement redirect-domain allowlist and validation | Security + Backend | 14 | 2026-09-14 12:00 | 2026-09-18 12:00 | Unknown, non-HTTPS and malformed redirects are blocked | Not Started | P0
QA-201 | Provider failure and partial-result security tests | QA | 8 | 2026-09-14 12:00 | 2026-09-18 12:00 | One failed provider does not hide successful results | Not Started | P0
SPRINT REVIEW BOX
Review Date | 2026-09-18 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Pending | Completion | 0% | Reviewer | Product Owner
Actual Result | Enter the demonstrated sprint outcome
Decision / Follow-up | Enter accepted changes, carry-over items and owner

## Sprint 3
Sprint 3 — Aggregation correctness
Matching offers are grouped accurately without merging different journeys.
Start Date | 2026-09-21 12:00 | End Date | 2026-10-02 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 80
EXPECTED SPRINT RESULT — Exact matching flights group into seller options; distinct or expired journeys remain separate.
SPRINT CONTEXT
A provider may return several timings, and several providers may return the same itinerary. This sprint preserves distinct journeys while grouping only exact itinerary matches into comparable seller options.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G3.1 | Expand itinerary fingerprint coverage |  |  | Codeshare, time-zone, terminal and overnight cases are covered |  |  |  | FL-021 | Pending
G3.2 | Verify exact-match itinerary grouping |  |  | Same flight from two providers appears once |  |  |  | FL-022 | Pending
G3.3 | Prevent near-match itinerary collisions |  |  | Different flight numbers/dates/connections never merge |  |  |  | FL-023 | Pending
G3.4 | Normalize currencies while preserving source values |  |  | Comparison is consistent and auditable |  |  |  | FL-024 | Pending
G3.5 | Define transparent seller ordering |  |  | Ordering considers price, freshness and disclosure completeness |  |  |  | FL-025 | Pending
G3.6 | Add sanitized provider contract fixtures |  |  | Provider normalizers are repeatably tested |  |  |  | FL-073 | Pending
G3.7 | Expired and duplicate offer regression suite |  |  | Expired offers cannot set the starting price |  |  |  | QA-301 | Pending
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-09-21 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-10-02 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-10-02 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-021 | Expand itinerary fingerprint coverage | Backend | 16 | 2026-09-21 12:00 | 2026-09-25 12:00 | Codeshare, time-zone, terminal and overnight cases are covered | Not Started | P0
FL-022 | Verify exact-match itinerary grouping | Backend | 12 | 2026-09-21 12:00 | 2026-09-25 12:00 | Same flight from two providers appears once | Not Started | P0
FL-023 | Prevent near-match itinerary collisions | Backend + QA | 14 | 2026-09-21 12:00 | 2026-09-25 12:00 | Different flight numbers/dates/connections never merge | Not Started | P0
FL-024 | Normalize currencies while preserving source values | Backend | 12 | 2026-09-28 12:00 | 2026-10-02 12:00 | Comparison is consistent and auditable | Not Started | P1
FL-025 | Define transparent seller ordering | Product + Backend | 10 | 2026-09-28 12:00 | 2026-10-02 12:00 | Ordering considers price, freshness and disclosure completeness | Not Started | P1
FL-073 | Add sanitized provider contract fixtures | QA | 10 | 2026-09-28 12:00 | 2026-10-02 12:00 | Provider normalizers are repeatably tested | Not Started | P1
QA-301 | Expired and duplicate offer regression suite | QA | 6 | 2026-09-28 12:00 | 2026-10-02 12:00 | Expired offers cannot set the starting price | Not Started | P0
SPRINT REVIEW BOX
Review Date | 2026-10-02 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Pending | Completion | 0% | Reviewer | Product Owner
Actual Result | Enter the demonstrated sprint outcome
Decision / Follow-up | Enter accepted changes, carry-over items and owner

## Sprint 4
Sprint 4 — Results experience and group usefulness
Travelers can quickly understand, compare and share the strongest options.
Start Date | 2026-10-05 12:00 | End Date | 2026-10-16 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 78
EXPECTED SPRINT RESULT — Compact accessible results clearly explain flight tradeoffs and support Trip Space planning.
SPRINT CONTEXT
The results page must help solo and group travelers make a decision quickly. This sprint improves hierarchy, explanations, accessibility, responsive behavior, sharing, and post-booking Trip Space usefulness.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G4.1 | Add search freshness and provider coverage summary |  |  | Users understand coverage and last checked state |  |  |  | FL-033 | Pending
G4.2 | Present itinerary with provider count and starting price |  |  | One card communicates the essential decision |  |  |  | FL-040 | Pending
G4.3 | Keep materially weaker alternatives collapsed |  |  | Strong results lead; alternatives remain discoverable |  |  |  | FL-042 | Pending
G4.4 | Explain Rovvy recommendation reasons |  |  | Recommendation logic is understandable |  |  |  | FL-043 | Pending
G4.5 | Design confirmed-flight attachment to Trip Space |  |  | External booking can be recorded without Rovvy servicing it |  |  |  | FL-060 | Pending
G4.6 | Accessibility and responsive visual regression |  |  | Keyboard, mobile and no-overflow requirements pass |  |  |  | FL-072 | Pending
G4.7 | Usability review with solo and group scenarios |  |  | Review findings and decisions are recorded |  |  |  | UX-401 | Pending
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-10-05 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-10-16 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-10-16 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-033 | Add search freshness and provider coverage summary | Frontend | 10 | 2026-10-05 12:00 | 2026-10-09 12:00 | Users understand coverage and last checked state | Not Started | P1
FL-040 | Present itinerary with provider count and starting price | Frontend | 14 | 2026-10-05 12:00 | 2026-10-09 12:00 | One card communicates the essential decision | Not Started | P0
FL-042 | Keep materially weaker alternatives collapsed | Frontend | 8 | 2026-10-05 12:00 | 2026-10-09 12:00 | Strong results lead; alternatives remain discoverable | Not Started | P1
FL-043 | Explain Rovvy recommendation reasons | Product + Frontend | 10 | 2026-10-12 12:00 | 2026-10-16 12:00 | Recommendation logic is understandable | Not Started | P1
FL-060 | Design confirmed-flight attachment to Trip Space | Product + Full Stack | 18 | 2026-10-12 12:00 | 2026-10-16 12:00 | External booking can be recorded without Rovvy servicing it | Not Started | P1
FL-072 | Accessibility and responsive visual regression | QA + Frontend | 12 | 2026-10-12 12:00 | 2026-10-16 12:00 | Keyboard, mobile and no-overflow requirements pass | Not Started | P1
UX-401 | Usability review with solo and group scenarios | Product | 6 | 2026-10-12 12:00 | 2026-10-16 12:00 | Review findings and decisions are recorded | Not Started | P1
SPRINT REVIEW BOX
Review Date | 2026-10-16 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Pending | Completion | 0% | Reviewer | Product Owner
Actual Result | Enter the demonstrated sprint outcome
Decision / Follow-up | Enter accepted changes, carry-over items and owner

## Sprint 5
Sprint 5 — First authorized external source
Activate one genuine redirect-capable provider or metasearch feed in evaluation mode.
Start Date | 2026-10-19 12:00 | End Date | 2026-10-30 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 80
EXPECTED SPRINT RESULT — One authorized source returns real/test offers with an itinerary-specific external handoff.
SPRINT CONTEXT
Rovvy needs one lawful, provider-approved data source before presenting real offers. This sprint is deliberately limited to an adapter foundation and one authorized evaluation integration; named providers are not shown until permission and credentials exist.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G5.1 | Complete the provider-neutral redirect adapter and authorization gate |  |  | A reusable adapter requires permission, environment, freshness, branding, rate-limit and handoff metadata before activation. |  |  |  | FL-050, PR-501, SEC-501 | Pending
G5.2 | Connect and verify one authorized evaluation provider |  |  | One approved source returns genuine evaluation offers, degrades safely and redirects to an itinerary-specific provider page. |  |  |  | FL-051, QA-501, OBS-501, DOC-501 | Pending
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-10-19 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-10-30 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-10-30 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-050 | Finalize redirect-only provider adapter template | Backend | 14 | 2026-10-19 12:00 | 2026-10-23 12:00 | Adapter contract requires valid handoff metadata | Not Started | P0
FL-051 | Integrate selected authorized evaluation feed | Backend | 24 | 2026-10-19 12:00 | 2026-10-23 12:00 | Authorized offers enter the coordinator | Blocked - Access | P1
PR-501 | Document provider permission and branding requirements | Product | 8 | 2026-10-19 12:00 | 2026-10-23 12:00 | Access evidence and obligations are auditable | Blocked - Access | P0
SEC-501 | Secure credentials and redact provider errors | Security + Backend | 10 | 2026-10-26 12:00 | 2026-10-30 12:00 | Secrets never reach client or logs | Not Started | P0
QA-501 | Provider contract and redirect tests | QA | 12 | 2026-10-26 12:00 | 2026-10-30 12:00 | Sanitized responses and safe handoffs pass | Blocked - Access | P0
OBS-501 | Provider latency, failure and rate-limit telemetry | Backend | 8 | 2026-10-26 12:00 | 2026-10-30 12:00 | Evaluation behavior is measurable | Not Started | P1
DOC-501 | Provider integration runbook | Product + Engineering | 4 | 2026-10-26 12:00 | 2026-10-30 12:00 | Next providers can follow a repeatable process | Not Started | P1
SPRINT REVIEW BOX
Review Date | 2026-10-30 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Pending | Completion | 0% | Reviewer | Product Owner
Actual Result | Enter the demonstrated sprint outcome
Decision / Follow-up | Enter accepted changes, carry-over items and owner

## Sprint 6
Sprint 6 — Release hardening and evidence package
Produce a stable non-commercial Flights preview ready for provider discussions.
Start Date | 2026-11-02 12:00 | End Date | 2026-11-13 12:00 | Workdays | 10 | Work Hours | 9:00 AM–5:00 PM CT | Planned Hours | 70
EXPECTED SPRINT RESULT — Rovvy demonstrates trustworthy comparison without internal booking, commissions or misleading data.
SPRINT CONTEXT
The non-commercial preview must be stable enough for demonstrations and provider discussions. This sprint proves security, resilience, performance, disclosure quality, operational readiness, and release ownership.
Goal ID | Feature Goal |  |  | Result / Evidence |  |  |  | Related Items | Goal Review
G6.1 | Create one release test command and CI quality gate |  |  | All P0 flight tests run consistently before release. |  |  |  | FL-070 | Pending
G6.2 | Complete redirect, credential, logging and error security review |  |  | No critical security issue remains and secrets never reach users or logs. |  |  |  | SEC-601 | Pending
G6.3 | Verify concurrent-provider performance |  |  | Timeouts, provider deadlines and partial results meet agreed targets. |  |  |  | PERF-601 | Pending
G6.4 | Prove empty, stale, expired, timeout and partial-result behavior |  |  | End-to-end evidence demonstrates safe degradation for every critical failure mode. |  |  |  | QA-601 | Pending
G6.5 | Prepare the product demonstration script |  |  | The redirect-only experience can be shown consistently without implying live booking. |  |  |  | DOC-601 | Pending
G6.6 | Prepare the provider architecture and evidence brief |  |  | Potential partners can understand the data flow, controls and integration contract. |  |  |  | DOC-601 | Pending
G6.7 | Approve privacy, terms and development-preview disclosures |  |  | Public wording accurately explains Rovvy's role and the provider's responsibility. |  |  |  | LEGAL-601 | Pending
G6.8 | Complete Product Owner release and rollback decision |  |  | The release decision, unresolved risks, rollback steps and accountable owners are recorded. |  |  |  | REL-601 | Pending
Ceremony / Work Block | Date or Recurrence | Time (CT) | Duration | Required Result | Ceremony / Work Block | Date | Time (CT) | Duration | Required Result
Sprint Planning | 2026-11-02 12:00 | 9:00–11:00 AM | 2 | Sprint goal, scope, owners and dependencies confirmed | Sprint Review | 2026-11-13 12:00 | 2:00–3:30 PM | 1.5 | Working increment demonstrated and result accepted/rejected
Daily Scrum | Every working day | 9:15–9:30 AM | 0.25 | Blockers and next 24-hour commitments recorded | Retrospective | 2026-11-13 12:00 | 3:30–4:30 PM | 1 | One improvement action assigned for next sprint
ID | Work Item | Owner | Est. Hours | Planned Start | Planned End | Expected Output / Result | Status | Priority | Review Notes
FL-070 | Consolidate flight tests into a release gate | QA + DevOps | 14 | 2026-11-02 12:00 | 2026-11-06 12:00 | One command/CI gate verifies Flights | Not Started | P0
SEC-601 | Security review of redirects, credentials and logs | Security | 10 | 2026-11-02 12:00 | 2026-11-06 12:00 | No critical flight security issue remains | Not Started | P0
PERF-601 | Concurrent provider performance verification | Backend | 10 | 2026-11-02 12:00 | 2026-11-06 12:00 | Timeouts and partial results meet targets | Not Started | P1
QA-601 | End-to-end failure and expiry scenarios | QA | 14 | 2026-11-09 12:00 | 2026-11-13 12:00 | Empty, stale, timeout and partial cases pass | Not Started | P0
DOC-601 | Prepare demo script and provider architecture brief | Product | 10 | 2026-11-09 12:00 | 2026-11-13 12:00 | Provider-facing evidence package is complete | Not Started | P1
LEGAL-601 | Review development, privacy and redirect disclosures | Product + Counsel | 6 | 2026-11-09 12:00 | 2026-11-13 12:00 | Public preview language is approved | Blocked - Review | P0
REL-601 | Product Owner release review and rollback checklist | Product + DevOps | 6 | 2026-11-09 12:00 | 2026-11-13 12:00 | Release decision and rollback steps are recorded | Not Started | P0
SPRINT REVIEW BOX
Review Date | 2026-11-13 12:00 | Review Time | 2:00–3:30 PM CT | Result Status | Pending | Completion | 0% | Reviewer | Product Owner
Actual Result | Enter the demonstrated sprint outcome
Decision / Follow-up | Enter accepted changes, carry-over items and owner

## Master Backlog
Flights Master Backlog
Editable source of planned work across all six sprints
Sprint | ID | Work Item | Owner | Hours | Start | End | Expected Result | Status | Priority
Sprint 1 | FL-001 | Make redirect-only behavior the single public Flights path | Product + Frontend | 14 | 2026-08-24 12:00 | 2026-09-04 12:00 | Public comparison journey never enters Rovvy checkout | Complete | P0
Sprint 1 | FL-002 | Disable internal checkout entry points and booking CTAs | Frontend | 14 | 2026-08-24 12:00 | 2026-09-04 12:00 | No public link reaches travelers, extras, review or payment | Complete | P0
Sprint 1 | FL-003 | Add consistent development-preview disclosure | Product + Frontend | 8 | 2026-08-24 12:00 | 2026-09-04 12:00 | Test status is visible before seller selection | Complete | P0
Sprint 1 | FL-004 | Allow guest comparison and provider handoff | Frontend | 10 | 2026-08-24 12:00 | 2026-09-04 12:00 | Authentication is not required to compare or redirect | Complete | P0
Sprint 1 | FL-041 | Replace booking language with comparison language | Product | 10 | 2026-08-24 12:00 | 2026-09-04 12:00 | All public copy uses Compare providers / Continue to provider | Complete | P0
Sprint 1 | FL-044 | Add provider-owned payment and support disclosure | Product + QA | 8 | 2026-08-24 12:00 | 2026-09-04 12:00 | Responsibility is clear beside every future redirect | Complete | P0
Sprint 1 | QA-101 | Regression tests for prohibited checkout paths and copy | QA | 8 | 2026-08-24 12:00 | 2026-09-04 12:00 | Automated tests prevent aggregator/OTA regression | Complete | P0
Sprint 2 | FL-010 | Enforce provider activation gate | Backend | 14 | 2026-09-07 12:00 | 2026-09-18 12:00 | Only configured + enabled + authorized + actionable sellers appear | Not Started | P0
Sprint 2 | FL-011 | Separate registered, configured, enabled and actionable states | Backend | 10 | 2026-09-07 12:00 | 2026-09-18 12:00 | Provider directory accurately reports lifecycle state | Not Started | P0
Sprint 2 | FL-012 | Block non-actionable seller prices from selection | Backend + Frontend | 10 | 2026-09-07 12:00 | 2026-09-18 12:00 | Unavailable sellers have no Continue action | Not Started | P0
Sprint 2 | FL-013 | Add authorization type and terms-review metadata | Product + Backend | 10 | 2026-09-07 12:00 | 2026-09-18 12:00 | Every production provider has auditable authorization metadata | Not Started | P1
Sprint 2 | FL-045 | Separate test and live seller presentation | Frontend | 10 | 2026-09-07 12:00 | 2026-09-18 12:00 | Sandbox results cannot visually impersonate live inventory | Not Started | P0
Sprint 2 | FL-071 | Implement redirect-domain allowlist and validation | Security + Backend | 14 | 2026-09-07 12:00 | 2026-09-18 12:00 | Unknown, non-HTTPS and malformed redirects are blocked | Not Started | P0
Sprint 2 | QA-201 | Provider failure and partial-result security tests | QA | 8 | 2026-09-07 12:00 | 2026-09-18 12:00 | One failed provider does not hide successful results | Not Started | P0
Sprint 3 | FL-021 | Expand itinerary fingerprint coverage | Backend | 16 | 2026-09-21 12:00 | 2026-10-02 12:00 | Codeshare, time-zone, terminal and overnight cases are covered | Not Started | P0
Sprint 3 | FL-022 | Verify exact-match itinerary grouping | Backend | 12 | 2026-09-21 12:00 | 2026-10-02 12:00 | Same flight from two providers appears once | Not Started | P0
Sprint 3 | FL-023 | Prevent near-match itinerary collisions | Backend + QA | 14 | 2026-09-21 12:00 | 2026-10-02 12:00 | Different flight numbers/dates/connections never merge | Not Started | P0
Sprint 3 | FL-024 | Normalize currencies while preserving source values | Backend | 12 | 2026-09-21 12:00 | 2026-10-02 12:00 | Comparison is consistent and auditable | Not Started | P1
Sprint 3 | FL-025 | Define transparent seller ordering | Product + Backend | 10 | 2026-09-21 12:00 | 2026-10-02 12:00 | Ordering considers price, freshness and disclosure completeness | Not Started | P1
Sprint 3 | FL-073 | Add sanitized provider contract fixtures | QA | 10 | 2026-09-21 12:00 | 2026-10-02 12:00 | Provider normalizers are repeatably tested | Not Started | P1
Sprint 3 | QA-301 | Expired and duplicate offer regression suite | QA | 6 | 2026-09-21 12:00 | 2026-10-02 12:00 | Expired offers cannot set the starting price | Not Started | P0
Sprint 4 | FL-033 | Add search freshness and provider coverage summary | Frontend | 10 | 2026-10-05 12:00 | 2026-10-16 12:00 | Users understand coverage and last checked state | Not Started | P1
Sprint 4 | FL-040 | Present itinerary with provider count and starting price | Frontend | 14 | 2026-10-05 12:00 | 2026-10-16 12:00 | One card communicates the essential decision | Not Started | P0
Sprint 4 | FL-042 | Keep materially weaker alternatives collapsed | Frontend | 8 | 2026-10-05 12:00 | 2026-10-16 12:00 | Strong results lead; alternatives remain discoverable | Not Started | P1
Sprint 4 | FL-043 | Explain Rovvy recommendation reasons | Product + Frontend | 10 | 2026-10-05 12:00 | 2026-10-16 12:00 | Recommendation logic is understandable | Not Started | P1
Sprint 4 | FL-060 | Design confirmed-flight attachment to Trip Space | Product + Full Stack | 18 | 2026-10-05 12:00 | 2026-10-16 12:00 | External booking can be recorded without Rovvy servicing it | Not Started | P1
Sprint 4 | FL-072 | Accessibility and responsive visual regression | QA + Frontend | 12 | 2026-10-05 12:00 | 2026-10-16 12:00 | Keyboard, mobile and no-overflow requirements pass | Not Started | P1
Sprint 4 | UX-401 | Usability review with solo and group scenarios | Product | 6 | 2026-10-05 12:00 | 2026-10-16 12:00 | Review findings and decisions are recorded | Not Started | P1
Sprint 5 | FL-050 | Finalize redirect-only provider adapter template | Backend | 14 | 2026-10-19 12:00 | 2026-10-30 12:00 | Adapter contract requires valid handoff metadata | Not Started | P0
Sprint 5 | FL-051 | Integrate selected authorized evaluation feed | Backend | 24 | 2026-10-19 12:00 | 2026-10-30 12:00 | Authorized offers enter the coordinator | Blocked - Access | P1
Sprint 5 | PR-501 | Document provider permission and branding requirements | Product | 8 | 2026-10-19 12:00 | 2026-10-30 12:00 | Access evidence and obligations are auditable | Blocked - Access | P0
Sprint 5 | SEC-501 | Secure credentials and redact provider errors | Security + Backend | 10 | 2026-10-19 12:00 | 2026-10-30 12:00 | Secrets never reach client or logs | Not Started | P0
Sprint 5 | QA-501 | Provider contract and redirect tests | QA | 12 | 2026-10-19 12:00 | 2026-10-30 12:00 | Sanitized responses and safe handoffs pass | Blocked - Access | P0
Sprint 5 | OBS-501 | Provider latency, failure and rate-limit telemetry | Backend | 8 | 2026-10-19 12:00 | 2026-10-30 12:00 | Evaluation behavior is measurable | Not Started | P1
Sprint 5 | DOC-501 | Provider integration runbook | Product + Engineering | 4 | 2026-10-19 12:00 | 2026-10-30 12:00 | Next providers can follow a repeatable process | Not Started | P1
Sprint 6 | FL-070 | Consolidate flight tests into a release gate | QA + DevOps | 14 | 2026-11-02 12:00 | 2026-11-13 12:00 | One command/CI gate verifies Flights | Not Started | P0
Sprint 6 | SEC-601 | Security review of redirects, credentials and logs | Security | 10 | 2026-11-02 12:00 | 2026-11-13 12:00 | No critical flight security issue remains | Not Started | P0
Sprint 6 | PERF-601 | Concurrent provider performance verification | Backend | 10 | 2026-11-02 12:00 | 2026-11-13 12:00 | Timeouts and partial results meet targets | Not Started | P1
Sprint 6 | QA-601 | End-to-end failure and expiry scenarios | QA | 14 | 2026-11-02 12:00 | 2026-11-13 12:00 | Empty, stale, timeout and partial cases pass | Not Started | P0
Sprint 6 | DOC-601 | Prepare demo script and provider architecture brief | Product | 10 | 2026-11-02 12:00 | 2026-11-13 12:00 | Provider-facing evidence package is complete | Not Started | P1
Sprint 6 | LEGAL-601 | Review development, privacy and redirect disclosures | Product + Counsel | 6 | 2026-11-02 12:00 | 2026-11-13 12:00 | Public preview language is approved | Blocked - Review | P0
Sprint 6 | REL-601 | Product Owner release review and rollback checklist | Product + DevOps | 6 | 2026-11-02 12:00 | 2026-11-13 12:00 | Release decision and rollback steps are recorded | Not Started | P0