ROVVY

Six-Month Product, Market
and Company Execution Plan

26 weeks from product coherence to controlled beta and investor readiness

PRODUCT MISSION A trusted travel companion for people traveling solo, coordinating with an existing group, or safely finding and joining compatible travelers.

Planning horizon: 10 August 2026 – 7 February 2027

Prepared as an operating roadmap for founders, product, engineering, design, growth, safety, and investors

HOW TO USE THIS PLAN

Purpose, assumptions, and decision discipline

CORE ASSUMPTION Rovvy wins by coordinating the human reality of travel—not by becoming another undifferentiated booking marketplace.

Audience: Founders, product and engineering leads, design, growth, operations, trust and safety, advisors, and prospective investors.

Cadence: Every week ends with a review of shipped outcomes, user evidence, quality metrics, risks, and the next gate.

Segments: Metrics must remain separated for solo travelers, existing groups, and travelers seeking to join a new group.

Scope rule: No work enters the critical path without a defined problem, owner, user outcome, metric, and acceptance test.

Release rule: Safety, privacy, authorization, financial integrity, and recovery gates outrank calendar commitments.

Evidence rule: Behavioral data and observed usability carry more weight than feature count, compliments, or founder preference.

Brand rule: Preserve Rovvy teal, navy, mint, typography, tone, and recognizable identity across every surface.

Planning rule: This is a living operating document; revise sequence when evidence changes, but record the reason and expected impact.

PRODUCT STRATEGY

The three-sided traveler promise

## Traveling solo

Useful before a network exists

Discover relevant places, build a lightweight plan, navigate confidently, save context, and get assistance during the trip.

## Traveling with an existing group

One shared operating layer

Coordinate decisions, itinerary, people, bookings, meet points, notifications, and money without fragmented chats and spreadsheets.

## Joining new travelers or groups

Compatibility with accountable trust

Understand the trip and people, request access transparently, set boundaries, and retain safety controls before and after joining.

SHARED PLATFORM ADVANTAGE The same identity, trip context, map, plan, communication, safety, and payment records can support all three modes while each mode keeps a distinct activation journey.

POSITIONING

Market wedge and strategic boundaries

## Positioning statement

For travelers who need confidence and coordination before and during a trip, Rovvy is a travel companion that connects discovery, live context, group decisions, shared plans, people, and money. Unlike booking-first tools or generic group chat, Rovvy organizes the trip relationship itself.

Initial wedge: Small leisure groups and socially open travelers planning multi-day trips, where coordination pain and trust questions are both visible.

Do now: Discovery, trip workspaces, collaboration, bookings visibility, expenses, live assistance, joining workflows, safety, and measurable onboarding.

Do later: Deep transaction fulfillment, broad marketplace supply, complex loyalty programs, autonomous AI actions, and native apps without validated demand.

Never compromise: Location privacy, clear membership boundaries, financial auditability, consent, safety escalation, and honest AI behavior.

Competitive frame: Compete on integrated coordination and trust, not on inventory breadth or lowest-price search.

Investor proof: Show segment-specific activation, collaborative usage, invite conversion, repeated trip value, safety readiness, and a credible monetization path.

SIX-MONTH OUTCOMES

What must be demonstrably true by Week 26

Coherent product: Every active route follows one Rovvy design system and a clear Explore / Live / Trips / Connect architecture.

Three activations: Each traveler mode has a short, instrumented path to first value and its own conversion baseline.

Collaborative value: Groups repeatedly use decisions, itinerary, people, bookings, and money in a shared trip context.

Trustworthy connection: Join-a-group pilots operate with visibility controls, reporting, blocking, moderation, and response runbooks.

Reliable operations: Core journeys meet agreed performance, accessibility, security, backup, monitoring, and incident standards.

Market evidence: Closed alpha and controlled beta cohorts generate retention, invitation, willingness-to-pay, and partner evidence.

Investment readiness: Rovvy has an evidence-led narrative, 12-month roadmap, hiring plan, use of funds, and explicit strategic decisions.

END-STATE TEST A founder should be able to demonstrate a complete solo journey, a complete existing-group journey, and a safe join-a-group journey using real product behavior—not presentation-only prototypes.

COMPANY SCORECARD

Metrics that govern weekly decisions

Activation: Intent selected → profile sufficient → first segment-specific value action completed.

Collaboration: Trips with two or more participating members and at least one shared decision or plan action.

Invite loop: Invites per activated organizer, acceptance rate, time to acceptance, and recipient activation.

Connect quality: Qualified previews, requests, organizer response time, acceptance, blocks/reports, and post-join health.

Retention: Repeat core action by segment in week one and week two; next-trip return when observable.

Reliability: Crash-free sessions, API error rate, p75/p95 latency, provider failure recovery, and notification delivery.

Trust: Safety incidents by severity, response SLA, privacy-control use, unauthorized access attempts, and resolution quality.

Business: Pricing interview evidence, upgrade intent, pilot partner contribution, acquisition source, and support cost.

All scorecard views must be filterable by traveler mode, acquisition cohort, platform, and release cohort. Aggregate growth must never hide a failing or unsafe segment.

OPERATING MODEL

Workstreams, ownership, and weekly rhythm

Product: Owns problem definition, sequencing, acceptance criteria, segment metrics, and decisions to continue/change/stop.

Engineering: Owns architecture, delivery, tests, security, performance, observability, data integrity, and reversible releases.

Design: Owns interaction coherence, responsive behavior, accessibility, research prototypes, and the fixed Rovvy identity.

Growth and market: Owns recruiting, interviews, messaging, referral experiments, partnerships, pricing evidence, and cohort quality.

Trust and operations: Owns consent, moderation, escalation, support, incident response, community standards, and launch capacity.

Founder: Owns strategic boundaries, capital allocation, hiring, investor communication, and final go/no-go decisions.

Monday: Confirm the weekly outcome, leading metric, release scope, owner, dependencies, and kill conditions.

Wednesday: Review working software and user evidence; remove blockers and prevent scope creep.

Friday: Demo shipped behavior, inspect scorecard and incidents, record learning, and approve the next gate.

ROADMAP OVERVIEW

Six phases across 26 weeks

| Phase | Timing | Primary outcome |
| --- | --- | --- |
| 1. Foundation | Weeks 1–4 | Baseline, design system, analytics, segmented onboarding |
| 2. Core utility | Weeks 5–8 | Solo discovery, Live, trip creation, invitations |
| 3. Group operating layer | Weeks 9–12 | Decisions, itinerary, bookings, money |
| 4. Connection and trust | Weeks 13–17 | Profiles, joining, safety, notifications, AI guardrails |
| 5. Evidence and business | Weeks 18–22 | Alpha, iteration, partners, pricing, growth loops |
| 6. Beta and investment | Weeks 23–26 | Hardening, launch operations, beta, retention, fundraising |

CRITICAL SEQUENCE Connection discovery does not scale before privacy and moderation; monetization does not lead before retention; beta does not open before reliability and incident readiness.

WEEK 01 / 26 • EXECUTION

Foundation and baseline

Confirm the product baseline, active routes, current quality, and six-month decision rules.

WEEKLY OUTCOME Confirm the product baseline, active routes, current quality, and six-month decision rules.

## Workstream commitments

Product: Inventory solo, group, and join-a-group journeys; freeze the active navigation model; identify duplicate and dead UI.

Engineering and data: Run lint, type-check, tests, accessibility scan, dependency review, and production configuration audit.

Design and accessibility: Create a route-by-route UI inventory using the existing Rovvy palette, typography, spacing, and component patterns.

Research and market: Recruit 12 design partners: four solo travelers, four existing groups, and four group-seeking travelers.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 01 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Approved baseline report; prioritized backlog; named owners; analytics event dictionary; zero ambiguity about MVP scope.

Evidence threshold: 100% active routes inventoried; 12 interviews scheduled; baseline funnel and reliability numbers recorded.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Scope inflation before evidence

Guardrail: No feature enters the six-month critical path without a user problem, owner, metric, and acceptance test.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 02 / 26 • EXECUTION

Design system and navigation

Make Rovvy feel like one product without changing its established brand identity.

WEEKLY OUTCOME Make Rovvy feel like one product without changing its established brand identity.

## Workstream commitments

Product: Finalize Explore, Live, Trips, Connect, and Profile information architecture with contextual access to bookings and money.

Engineering and data: Consolidate semantic design tokens and shared primitives; retain meaningful map, chart, transport, and status colors.

Design and accessibility: Standardize page headers, cards, buttons, forms, tabs, dialogs, empty states, and mobile navigation.

Research and market: Run five first-click tests on the new navigation and compare completion time with the baseline.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 02 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Shared UI primitives adopted by the highest-traffic screens; documented exceptions for immersive Live mode.

Evidence threshold: 90% first-click success on core destinations; no contrast failures in primary flows; no brand-color drift.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: A cosmetic redesign that ignores behavior

Guardrail: Accept UI work only when it reduces confusion, inconsistency, or task time.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 03 / 26 • EXECUTION

Analytics and consent

Build trustworthy measurement before optimizing acquisition or engagement.

WEEKLY OUTCOME Build trustworthy measurement before optimizing acquisition or engagement.

## Workstream commitments

Product: Define activation separately for solo, existing-group, and join-a-group users; add consent-aware tracking.

Engineering and data: Implement event schemas, server-side outcome events, privacy controls, retention limits, and dashboard-ready identifiers.

Design and accessibility: Design privacy explanations and location-sharing consent states in plain language.

Research and market: Test event naming and consent comprehension with six users; verify that declining optional analytics preserves core use.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 03 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Validated event stream for signup, profile completion, trip creation, invite, join request, first plan, and expense settlement.

Evidence threshold: >=95% event delivery in staging; duplicate rate <2%; all sensitive events pass privacy review.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Collecting precise location without sufficient purpose

Guardrail: Minimize data, make sharing time-bound, and log consent changes.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 04 / 26 • EXECUTION

Onboarding by travel mode

Give each traveler a short, relevant path to first value.

WEEKLY OUTCOME Give each traveler a short, relevant path to first value.

## Workstream commitments

Product: Introduce three onboarding intents: travel solo, plan with my group, or find compatible people/groups.

Engineering and data: Persist onboarding intent and progressive profile completion without blocking exploration.

Design and accessibility: Create concise onboarding screens, skip paths, progress feedback, and accessible validation.

Research and market: Usability-test all three paths with at least three participants per intent.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 04 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Users land in the correct home context with one clear next action and recoverable incomplete profiles.

Evidence threshold: >=70% onboarding completion; median completion under three minutes; <10% validation abandonment.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Asking for trust-heavy details too early

Guardrail: Collect only what is necessary for first value; defer sensitive fields.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 05 / 26 • EXECUTION

Solo discovery MVP

Make Rovvy immediately useful before a traveler has created or joined a group.

WEEKLY OUTCOME Make Rovvy immediately useful before a traveler has created or joined a group.

## Workstream commitments

Product: Strengthen destination discovery, activities, events, saved places, and lightweight day planning.

Engineering and data: Normalize explore data, improve empty/error handling, cache safe responses, and add observability for provider failures.

Design and accessibility: Unify discovery cards, filters, map/list transitions, save actions, and itinerary prompts.

Research and market: Run task tests for finding, comparing, saving, and revisiting an activity in an unfamiliar city.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 05 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A solo traveler can discover three relevant options, save one, and turn it into a plan without a group.

Evidence threshold: >=40% of activated solo users save an item; median discovery-to-save under five minutes.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Generic recommendations with no situational relevance

Guardrail: Start with reliable filters and context before heavy personalization.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 06 / 26 • EXECUTION

Live companion reliability

Turn Live into a dependable in-trip assistance surface rather than a visual demo.

WEEKLY OUTCOME Turn Live into a dependable in-trip assistance surface rather than a visual demo.

## Workstream commitments

Product: Prioritize nearby context, route clarity, saved places, meet points, and quick recovery when connectivity is weak.

Engineering and data: Harden geocoding, route providers, map loading, permissions, offline states, and battery-conscious location updates.

Design and accessibility: Preserve immersive Live styling while standardizing controls, panels, labels, and error feedback.

Research and market: Field-test walking and transit scenarios in two environments with permission denial and network loss cases.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 06 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Live launches quickly, explains its state, and always offers a safe fallback when data is unavailable.

Evidence threshold: Map usable p75 <3 seconds on supported networks; route failure recovery >=95%; zero blocked exits.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: False confidence from stale or incomplete location data

Guardrail: Show freshness, accuracy, provider state, and manual alternatives.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 07 / 26 • EXECUTION

Trip creation and planning

Make starting a trip simple enough for the organizer and understandable to every member.

WEEKLY OUTCOME Make starting a trip simple enough for the organizer and understandable to every member.

## Workstream commitments

Product: Streamline trip creation, dates, destination, visibility, group association, and first planning action.

Engineering and data: Validate state transitions, permissions, date constraints, and API errors; add idempotency where duplicate creation is possible.

Design and accessibility: Create a focused trip overview with next actions, progress, people, bookings, plans, and money.

Research and market: Observe four organizers creating a real or realistic trip and inviting their first collaborator.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 07 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A new organizer creates a trip and reaches a collaborative state in one uninterrupted session.

Evidence threshold: >=60% trip-creation completion; median under four minutes; duplicate-trip rate below 1%.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Overloading the initial form

Guardrail: Use progressive setup and move optional planning detail into the trip workspace.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 08 / 26 • EXECUTION

Invites and group activation

Make the invitation loop fast, clear, and measurable.

WEEKLY OUTCOME Make the invitation loop fast, clear, and measurable.

## Workstream commitments

Product: Improve invite links/codes, pending states, resend behavior, role clarity, and non-member previews.

Engineering and data: Secure invite tokens, rate-limit abuse, instrument delivery/acceptance, and handle expired or revoked invitations.

Design and accessibility: Design organizer feedback and recipient landing pages with the trip value visible before signup.

Research and market: Test inviter and recipient halves separately; include a traveler without an existing Rovvy account.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 08 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Organizers know exactly who has been invited, joined, declined, or needs follow-up.

Evidence threshold: >=35% invite acceptance within seven days; <5% invalid-link failures; supportable recovery for every state.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Invite friction hidden behind authentication

Guardrail: Preserve context through signup and return users to the exact invitation.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 09 / 26 • EXECUTION

Collaborative decisions

Reduce chat chaos by making group choices explicit and fair.

WEEKLY OUTCOME Reduce chat chaos by making group choices explicit and fair.

## Workstream commitments

Product: Connect polls to trip decisions for destination, date, activity, budget, and meeting choices.

Engineering and data: Harden voting rules, guest voting, auto-close behavior, notifications, and concurrency.

Design and accessibility: Show decision status, participation, deadlines, and the selected outcome inside the trip.

Research and market: Run a five-person planning simulation and measure time to reach a decision.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 09 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A group creates, votes, closes, and converts a decision into a plan without leaving Rovvy.

Evidence threshold: >=50% of active multi-member trips create one decision; >=65% invited members participate.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Polls become another disconnected feature

Guardrail: Every poll must attach to a trip context and produce a next action.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 10 / 26 • EXECUTION

Shared itinerary and ownership

Create a single source of truth for what the group is doing and who owns each action.

WEEKLY OUTCOME Create a single source of truth for what the group is doing and who owns each action.

## Workstream commitments

Product: Unify scheduled items, notes, meet points, reservations, assignments, and change visibility.

Engineering and data: Define ordering, timezone behavior, edit permissions, optimistic updates, and conflict resolution.

Design and accessibility: Design day views, agenda summaries, ownership labels, and mobile quick actions.

Research and market: Test a three-day itinerary with edits from organizer and member roles across time zones.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 10 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Members can answer what, when, where, and who without reading an external chat history.

Evidence threshold: >=50% of activated group trips add three itinerary items; edit failure rate <2%.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Timezone and concurrent-edit confusion

Guardrail: Store canonical times, display local context, and preserve change history.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 11 / 26 • EXECUTION

Bookings hub

Make travel reservations visible and actionable without pretending to be a full OTA.

WEEKLY OUTCOME Make travel reservations visible and actionable without pretending to be a full OTA.

## Workstream commitments

Product: Consolidate flights, hotels, buses, and routes under Trips > Bookings with manual and integration-ready records.

Engineering and data: Normalize booking data, protect confirmation details, and add provider-independent status models.

Design and accessibility: Create booking cards, traveler assignments, missing-detail prompts, and chronological grouping.

Research and market: Test adding and locating a booking during a simulated airport disruption.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 11 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: The group can see critical booking facts and ownership from one trip context.

Evidence threshold: >=30% of active trips add a booking; critical-detail retrieval under 20 seconds in testing.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Expanding prematurely into transaction fulfillment

Guardrail: Stay coordination-first until demand and partner economics are proven.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 12 / 26 • EXECUTION

Money and settlement

Make shared travel spending understandable, fair, and safe.

WEEKLY OUTCOME Make shared travel spending understandable, fair, and safe.

## Workstream commitments

Product: Unify expense capture, splits, balances, settlement suggestions, currencies, and activity history.

Engineering and data: Audit decimal precision, currency conversion, authorization, concurrency, migrations, and reconciliation tests.

Design and accessibility: Use clear payer/participant language, balance summaries, edit consequences, and accessible charts only where useful.

Research and market: Run realistic scenarios: equal split, custom split, multi-currency, refund, member removal, and correction.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 12 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Every balance is explainable from source expenses and changes are traceable.

Evidence threshold: 100% deterministic scenario reconciliation; zero unauthorized edits; calculation coverage on critical paths.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Financial trust loss from a single unexplained balance

Guardrail: Prioritize auditability and clarity above clever automation.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 13 / 26 • EXECUTION

Connect profiles and compatibility

Help travelers evaluate fit without reducing people to superficial matching scores.

WEEKLY OUTCOME Help travelers evaluate fit without reducing people to superficial matching scores.

## Workstream commitments

Product: Define opt-in travel preferences, pace, budget style, interests, languages, accessibility needs, and boundaries.

Engineering and data: Separate public, connection-only, and private fields; add moderation-ready profile controls.

Design and accessibility: Design respectful compatibility explanations and profile completeness cues without dark patterns.

Research and market: Interview group-seeking travelers about what creates confidence and what feels invasive.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 13 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A traveler can express enough context to make a safe, informed connection decision.

Evidence threshold: >=60% of Connect users complete core preference fields; privacy comprehension >=80% in testing.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Sensitive profiling or discriminatory filters

Guardrail: Use optional, user-controlled signals and review every filter for harm.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 14 / 26 • EXECUTION

Join-a-group workflow

Turn discovery into a transparent request, review, and acceptance process.

WEEKLY OUTCOME Turn discovery into a transparent request, review, and acceptance process.

## Workstream commitments

Product: Build browse, preview, request-to-join, organizer review, questions, approve/decline, and onboarding states.

Engineering and data: Harden trip-only versus group membership semantics, permissions, invite codes, and notification delivery.

Design and accessibility: Make expectations, visibility, cost, dates, participant count, and decision status clear before requesting.

Research and market: Run end-to-end simulations with applicant, organizer, accepted member, and declined applicant roles.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 14 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: No participant is surprised by what joining grants, exposes, costs, or requires.

Evidence threshold: >=20% qualified preview-to-request rate; median organizer response under 48 hours in pilot.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Treating access approval as sufficient trust

Guardrail: Pair joining with safety education, boundaries, and reporting controls.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 15 / 26 • EXECUTION

Trust, safety, and moderation

Make safety a product system, not a policy page added after growth.

WEEKLY OUTCOME Make safety a product system, not a policy page added after growth.

## Workstream commitments

Product: Add report, block, leave, remove, emergency guidance, community standards, and incident escalation paths.

Engineering and data: Implement evidence retention rules, moderation queues, access logging, rate limits, and abuse monitoring.

Design and accessibility: Place safety controls where incidents happen; use neutral language and avoid exposing reporters.

Research and market: Conduct tabletop exercises for harassment, impersonation, unsafe meetup, payment dispute, and compromised account.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 15 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A documented severity model, response SLA, owner rotation, and auditable case lifecycle exist before public matching.

Evidence threshold: 100% critical scenarios have a runbook; block/report accessible within two interactions.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Launching social discovery without operational capacity

Guardrail: Limit pilot size to what the moderation team can safely support.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 16 / 26 • EXECUTION

Notifications and communication

Deliver timely coordination without becoming another noisy group chat.

WEEKLY OUTCOME Deliver timely coordination without becoming another noisy group chat.

## Workstream commitments

Product: Prioritize invitations, decision deadlines, itinerary changes, meet points, safety events, and expense actions.

Engineering and data: Create preference controls, batching, deduplication, delivery status, retries, and channel fallbacks.

Design and accessibility: Design actionable notifications with clear source, trip context, urgency, and deep link.

Research and market: Test interruption tolerance and notification preferences across all three traveler modes.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 16 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Critical events reach the right person while low-value activity is summarized or muted.

Evidence threshold: >=90% critical delivery success; duplicate notifications <1%; opt-out reasons captured.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Notification fatigue destroys trust

Guardrail: Default to fewer high-value notifications and let users control channels.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 17 / 26 • EXECUTION

AI companion guardrails

Use AI where it reduces planning effort while keeping facts, consent, and control visible.

WEEKLY OUTCOME Use AI where it reduces planning effort while keeping facts, consent, and control visible.

## Workstream commitments

Product: Focus AI on trip summaries, option comparison, planning prompts, and contextual assistance—not autonomous commitments.

Engineering and data: Add grounding, provider citations where available, sensitive-data rules, rate controls, eval cases, and fallback behavior.

Design and accessibility: Clearly label generated content, allow editing, and show when information may be stale.

Research and market: Evaluate 100 representative prompts across solo, group, live, booking, money, and safety contexts.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 17 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: AI suggestions are reviewable, reversible, and never silently modify shared plans or financial data.

Evidence threshold: >=85% useful-response rating in curated evals; 0 critical safety-policy failures.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Hallucinated travel or safety information

Guardrail: Ground high-impact claims and route emergencies to authoritative sources.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 18 / 26 • EXECUTION

Closed alpha

Move from feature completion to observed, supported travel behavior.

WEEKLY OUTCOME Move from feature completion to observed, supported travel behavior.

## Workstream commitments

Product: Enroll 30-50 participants across the three segments and define weekly missions.

Engineering and data: Create release channels, feature flags, diagnostics, backup procedures, and fast rollback.

Design and accessibility: Add in-product feedback, bug-report context, and a lightweight alpha status surface.

Research and market: Run founder-led onboarding and two structured feedback sessions during the week.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 18 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Every alpha participant has a segment, intended journey, support channel, and consented research plan.

Evidence threshold: >=60% complete their segment activation; p1 bugs acknowledged within four hours.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Confusing compliments with evidence

Guardrail: Judge value by repeated behavior, task completion, and willingness to invite others.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 19 / 26 • EXECUTION

Alpha learning sprint

Convert observed friction into prioritized fixes instead of adding breadth.

WEEKLY OUTCOME Convert observed friction into prioritized fixes instead of adding breadth.

## Workstream commitments

Product: Repair the top activation, collaboration, and trust breakdowns found in alpha.

Engineering and data: Triage defects by severity and frequency; add regression tests before closing critical issues.

Design and accessibility: Polish only the journeys demonstrated to matter; remove or defer distracting surfaces.

Research and market: Conduct ten short playback interviews using real session evidence and support tickets.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 19 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A written continue/change/stop decision exists for each major product hypothesis.

Evidence threshold: Activation improves >=15% from alpha baseline; critical open defect count trends downward.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Founder preference overrides user evidence

Guardrail: Use the agreed scorecard and document exceptions explicitly.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 20 / 26 • EXECUTION

Partner and supply pilot

Test whether local and travel partners improve utility and distribution.

WEEKLY OUTCOME Test whether local and travel partners improve utility and distribution.

## Workstream commitments

Product: Define partner value for activities, host communities, accommodations, universities, and travel clubs.

Engineering and data: Create controlled partner metadata, attribution, lead tracking, and content-quality controls.

Design and accessibility: Build a lightweight partner profile or offer treatment consistent with Rovvy—not advertising clutter.

Research and market: Interview ten potential partners and pilot with two that fit the target traveler journeys.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 20 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A repeatable partner proposition, onboarding checklist, and measurable traveler benefit are documented.

Evidence threshold: Two pilots live; partner-sourced activation measurable; no pay-to-rank ambiguity.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Partnership work distracts from product-market fit

Guardrail: Choose partners only when they improve core traveler outcomes.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 21 / 26 • EXECUTION

Pricing and willingness to pay

Test monetization hypotheses without damaging early trust or network growth.

WEEKLY OUTCOME Test monetization hypotheses without damaging early trust or network growth.

## Workstream commitments

Product: Compare free coordination, organizer Pro, premium Live/AI assistance, and partner revenue hypotheses.

Engineering and data: Validate subscription states, entitlements, Stripe webhooks, cancellation, retries, and sandbox reconciliation.

Design and accessibility: Create honest upgrade messaging tied to outcomes; never lock safety or basic joining behind payment.

Research and market: Run pricing interviews and landing-page tests; do not infer willingness from compliments.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 21 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A pricing recommendation includes target buyer, value metric, free boundary, price range, and evidence strength.

Evidence threshold: >=15 pricing conversations; measurable intent signal; zero entitlement leakage in tests.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Monetizing before retention exists

Guardrail: Treat pricing as discovery unless repeat usage supports a paid beta.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 22 / 26 • EXECUTION

Growth loops and referrals

Grow through successful travel collaboration rather than paid acquisition alone.

WEEKLY OUTCOME Grow through successful travel collaboration rather than paid acquisition alone.

## Workstream commitments

Product: Improve invite, shared trip preview, post-trip recap, referral, and community ambassador loops.

Engineering and data: Add attribution that respects consent and avoids exposing private trip information.

Design and accessibility: Design share artifacts with safe defaults, clear audience controls, and Rovvy brand consistency.

Research and market: Test three messages with activated users and measure actual sharing, not stated preference.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 22 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: One primary organic loop is selected with a known trigger, receiver value, and conversion event.

Evidence threshold: Invite rate >=0.8 per activated organizer; referral acceptance improves week over week.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Viral mechanics leak private travel data

Guardrail: Default shared artifacts to minimum information and explicit audience selection.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 23 / 26 • EXECUTION

Performance, security, and accessibility

Prepare the product for a wider beta with measurable quality gates.

WEEKLY OUTCOME Prepare the product for a wider beta with measurable quality gates.

## Workstream commitments

Product: Close high-severity usability and accessibility defects across all active routes.

Engineering and data: Run dependency, auth, authorization, secret, rate-limit, database, backup, performance, and recovery reviews.

Design and accessibility: Verify keyboard, focus, contrast, responsive layout, reduced motion, and screen-reader behavior.

Research and market: Include users with accessibility needs and low-connectivity conditions in validation.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 23 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: No known critical security issue; recovery tested; active journeys meet the beta quality threshold.

Evidence threshold: Zero open p0/p1 security defects; WCAG AA on core flows; API p95 targets documented and met.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Shipping known high-impact defects to meet a date

Guardrail: Quality gates outrank calendar pressure for safety and data integrity.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 24 / 26 • EXECUTION

Beta readiness and operations

Make launch supportable, observable, and reversible.

WEEKLY OUTCOME Make launch supportable, observable, and reversible.

## Workstream commitments

Product: Finalize beta scope, eligibility, onboarding, help content, community standards, and feedback channels.

Engineering and data: Complete monitoring, alerts, incident response, backups, rollback, data export/deletion, and capacity tests.

Design and accessibility: Polish release notes, status messaging, support entry points, and known-limitation communication.

Research and market: Run a full launch rehearsal with product, engineering, safety, support, and founder roles.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 24 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: A signed go/no-go checklist, duty roster, escalation tree, and daily launch dashboard are ready.

Evidence threshold: All launch blockers closed; alert tests pass; support SLA and ownership confirmed.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Operational ambiguity during incidents

Guardrail: Every alert has an owner, threshold, runbook, and communication path.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 25 / 26 • EXECUTION

Controlled beta launch

Release to a bounded audience and learn without losing operational control.

WEEKLY OUTCOME Release to a bounded audience and learn without losing operational control.

## Workstream commitments

Product: Open access in cohorts across all three segments; preserve feature flags and eligibility controls.

Engineering and data: Monitor errors, latency, abuse, notification delivery, data consistency, and provider health continuously.

Design and accessibility: Resolve launch-critical comprehension issues and maintain consistent release communication.

Research and market: Hold daily user playback and support reviews; contact users who abandon critical steps.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 25 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: The beta operates within reliability and safety capacity while producing comparable cohort data.

Evidence threshold: Activation >=55%; week-one retained core action >=30%; no unresolved critical incident.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Scaling signups faster than support capacity

Guardrail: Increase cohorts only after the previous cohort clears quality gates.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?

WEEK 26 / 26 • EXECUTION

Retention, fundraising, and next-quarter decision

Turn six months of behavior into a defensible retention model and evidence-based investment plan.

WEEKLY OUTCOME Turn six months of behavior into a defensible retention model and evidence-based investment plan.

## Workstream commitments

Product: Identify the strongest repeat-value loop by segment; synthesize product proof, market wedge, business model, and next milestones.

Engineering and data: Build cohort views and document architecture health, security posture, scalability constraints, technical debt, and hiring needs.

Design and accessibility: Refine lifecycle experiences and prepare coherent investor demo flows using actual product evidence and Rovvy identity.

Research and market: Interview retained and churned users, then conduct advisory reviews and three investor-style rehearsals.

## Execution sequence

Monday: Confirm user problem, acceptance criteria, leading metric, responsible owner, dependencies, and release boundary.

Tuesday–Wednesday: Build the smallest end-to-end behavior, review working software early, and instrument the outcome—not only clicks.

Thursday: Run accessibility, permission, error, empty, loading, mobile, and recovery checks; conduct the scheduled user validation.

Friday: Release behind the appropriate control, inspect evidence, document decisions, and prepare the next gate.

WEEK 26 / 26 • CONTROL SHEET

Deliverables, evidence, risks, and exit gate

## Definition of done

Primary deliverable: Board-ready six-month review, north-star behavior, 12-month roadmap, hiring plan, use of funds, and go/change/stop decisions.

Evidence threshold: Week-two repeat action >=20% in the target cohort; validated traction narrative and next-quarter objectives approved.

Quality checks: No newly introduced lint, type, test, accessibility, authorization, privacy, or responsive-layout regression in the affected journey.

Documentation: Update decision log, event dictionary, acceptance evidence, known limitations, support notes, and the next dependency.

## Risk control

Most likely failure: Fundraising story or aggregate metrics outrun segment evidence

Guardrail: Lead with observed behavior and review all three traveler cohorts independently.

Rollback trigger: Any critical safety, privacy, financial-integrity, authorization, data-loss, or unrecoverable journey failure.

## Friday exit questions

Did the intended traveler complete the outcome in working software?

What behavior changed, and how strong is the evidence by segment?

What failed or surprised us, including support and safety signals?

What will we continue, change, stop, or defer next week?

Is the next gate safe, measurable, owned, and reversible?