## Live Tasks
Rovvy Live — feature and priority tracker
Reviewed 24 Sep 2026 · localhost:3000/live · Browser sample + source inspection. Complete in code does not mean production QA.
Items | 312 | Complete in code | 118 | Partial | 185 | Pending | 9 | Critical | 103
Same Explorer color key: red = Very hard; yellow = Critical or Partial; green = Complete in code; gray = Pending. Ratings are review judgments.
One row per separately assessable control, display, action or behavior. Filter Importance for cruciality. Evidence marked Code only needs runtime verification; counts are not readiness percentages.
ID | Workstream | Task / feature | Status | Importance | Difficulty | Acceptance / next action | Evidence / current finding | Dependency | Type | Why it matters / feedback
L001 | Map controls | Zoom-in control | Complete in code | Critical | Easy | Confirm button and keyboard activation at all zooms. | Browser: Visible and enabled below maximum zoom; Source: LiveMapZoomControl.tsx | See acceptance / next action | Graphic | Users need precise map scale.
L002 | Map controls | Zoom-out control | Complete in code | Critical | Easy | Confirm minimum zoom and disabled state. | Browser: Visible on loaded map; Source: LiveMapZoomControl.tsx | See acceptance / next action | Graphic | Users need regional context.
L003 | Map controls | Maximum-zoom disabled feedback | Complete in code | Important | Easy | Confirm state follows active map style cap. | Browser: Zoom-in button changed to Maximum zoom disabled at z14; Source: LiveMapZoomControl.tsx | See acceptance / next action | Graphic | Prevents a control that appears broken.
L004 | Map controls | Numeric zoom slider | Complete in code | Important | Moderate | Check drag and keyboard increments. | Browser: Visible with zoom value in accessibility tree; Source: LiveStripZoomScale.tsx | See acceptance / next action | Graphic | Gives direct scale control.
L005 | Map controls | Map scale tick strip | Complete in code | Later | Moderate | Check scale ticks at globe and street zoom. | Code only: LiveStripZoomScale.tsx | See acceptance / next action | Graphic | Helps interpret zoom level.
L006 | Map controls | Map-center coordinate readout | Complete in code | Important | Easy | Check readout updates after drag. | Browser: Chicago coordinates changed after map movement; Source: LiveMapAttributionStrip.tsx | See acceptance / next action | Graphic | Supports exact geographic orientation.
L007 | Map controls | North-bearing indicator | Complete in code | Important | Easy | Check angle matches rotated map. | Browser: Facing North control visible; Source: LiveMapCompass.tsx | See acceptance / next action | Graphic | Avoids directional confusion.
L008 | Map controls | Reset-north action | Complete in code | Important | Easy | Check map bearing resets to zero. | Code only: LiveMapCompass.tsx | See acceptance / next action | Graphic | Restores familiar orientation.
L009 | Map controls | Map pan interaction | Complete in code | Critical | Moderate | Test pointer and touch panning. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Foundation of area browsing.
L010 | Map controls | Wheel zoom interaction | Complete in code | Important | Moderate | Check scroll behavior and zoom cap. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Supports quick inspection.
L011 | Map controls | Pinch zoom interaction | Partial | Important | Moderate | Verify on a touch device. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Travelers frequently use phones.
L012 | Map controls | Map rotation interaction | Complete in code | Important | Moderate | Check rotation and compass synchronization. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Preserves orientation when rotating.
L013 | Map controls | Map pitch interaction | Complete in code | Later | Moderate | Check tilt limits and reset. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Makes 3D context usable.
L014 | Map controls | Fly-to selected place | Complete in code | Critical | Moderate | Confirm target remains visible beyond overlays. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Selected place must be findable.
L015 | Map controls | Fit route bounds | Complete in code | Important | Moderate | Check origin and destination fit with dock open. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Shows the full journey.
L016 | Map controls | Map fullscreen exit | Partial | Important | Moderate | Test keyboard exit and layout restoration. | Code only: LiveImmersiveChrome.tsx | See acceptance / next action | Graphic | Users need a reliable escape path.
L017 | Map visual rendering | Detailed road labels | Complete in code | Important | Moderate | Check labels at multiple zooms. | Browser: Chicago road labels rendered on map; Source: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Street names support wayfinding.
L018 | Map visual rendering | Detailed point-of-interest labels | Complete in code | Important | Moderate | Check tap target versus visible label. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Names support selection.
L019 | Map visual rendering | Detailed house numbers | Complete in code | Important | Moderate | Check zoom-14 threshold and density. | Browser: House numbers rendered at z14; Source: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Address precision matters.
L020 | Map visual rendering | Clean reduced-label rendering | Complete in code | Later | Moderate | Check clutter reduction in dense city. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | A quieter alternative map.
L021 | Map visual rendering | Clean house-number threshold | Complete in code | Later | Moderate | Check zoom-15 threshold. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Keeps clean mode useful near an address.
L022 | Map visual rendering | Satellite imagery tile rendering | Partial | Later | Hard | Open and verify actual imagery and attribution. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Useful context when streets are unclear.
L023 | Map visual rendering | Terrain elevation contour rendering | Partial | Later | Hard | Open and verify contours in hilly terrain. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Outdoor context depends on accurate contours.
L024 | Map visual rendering | Hybrid road casing | Complete in code | Later | Hard | Check contrast over bright and dark imagery. | Code only: live-hybrid-roads-sync.ts | See acceptance / next action | Graphic | Makes roads legible on satellite.
L025 | Map visual rendering | Hybrid place labels | Partial | Later | Moderate | Verify labels render after style switch. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | Graphic | Hybrid map needs readable names.
L026 | Map visual rendering | Base-layer selection persistence | Complete in code | Important | Moderate | Reload after each selectable style. | Code only: live-map-layer-preference.ts | See acceptance / next action | Graphic | Prevents surprise map changes.
L027 | Map visual rendering | Style prefetch for faster switching | Complete in code | Important | Moderate | Time first and repeat switches. | Code only: live-map-style-prefetch.ts | See acceptance / next action | Graphic | Reduces blank map intervals.
L028 | Map visual rendering | Local development tile fallback | Complete in code | Critical | Hard | Test unavailable configured tile host. | Code only: live-openfreemap-tile-fallback.ts | See acceptance / next action | Graphic | Keeps the map usable on localhost.
L029 | Map visual rendering | Overlay restoration after style switch | Partial | Critical | Hard | Toggle style with route and pins active. | Code only: LiveMapComponent.tsx | See acceptance / next action | Graphic | Switching style must retain travel context.
L030 | Map visual rendering | Globe projection at low zoom | Complete in code | Later | Hard | Test flat-to-globe transition. | Code only: live-map-globe.ts | See acceptance / next action | Graphic | Provides world-scale orientation.
L031 | Map visual rendering | Globe background / atmosphere | Complete in code | Later | Moderate | Check contrast and loading performance. | Code only: live-map-globe.ts | See acceptance / next action | Graphic | Adds visual context without obscuring data.
L032 | Map visual rendering | Globe sunlight position | Complete in code | Later | Hard | Check day/night lighting at known times. | Code only: live-globe-sun.ts | See acceptance / next action | Graphic | Lighting should match geography.
L033 | Layer controls | Layers panel open and close | Complete in code | Important | Easy | Test button and outside click. | Browser: Opened layer menu and closed it; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Map settings must be easy to reach.
L034 | Layer controls | Selected base-layer indicator | Complete in code | Important | Easy | Check indicator matches rendered map. | Browser: Detailed option selected in layer menu; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Prevents confusing layer state.
L035 | Layer controls | Detailed layer selector | Complete in code | Important | Moderate | Select and verify labels render. | Browser: Detailed option visible; rendered map matched; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Core street view choice.
L036 | Layer controls | Clean layer selector | Complete in code | Important | Moderate | Select and verify minimal map renders. | Browser: Clean option visible; not selected; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Provides a lighter map.
L037 | Layer controls | Satellite layer selector | Partial | Later | Hard | Select and verify actual imagery. | Browser: Satellite option visible; not selected; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Aerial view only helps if tiles load.
L038 | Layer controls | Terrain layer selector | Partial | Later | Hard | Select and verify elevation view. | Browser: Terrain option visible; not selected; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Topography should match picker claim.
L039 | Layer controls | Hybrid layer selector | Partial | Later | Hard | Select and verify imagery plus roads. | Browser: Hybrid option visible; not selected; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Avoids selected/rendered mismatch.
L040 | Layer controls | Dark layer product gate | Pending | Later | Easy | Keep hidden until approved and QA complete. | Code only: live-map-layer-preference.ts | See acceptance / next action | UI extension | This mode was intentionally disabled.
L041 | Layer controls | Saved-pins layer toggle | Complete in code | Important | Moderate | Toggle and verify pin visibility. | Browser: My saves option visible with device-only help; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Users control personal map clutter.
L042 | Layer controls | Discovery layer toggle | Partial | Critical | Hard | Retry failed overlay and show result. | Browser: Parks & capitals showed layer unavailable · try again; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Current session showed unavailable state.
L043 | Layer controls | Report layer toggle | Partial | Important | Moderate | Toggle with known report data. | Browser: Reports option visible with 2-hour help; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Users control live-report clutter.
L044 | Layer controls | Travel overlay toggle | Complete in code | Later | Moderate | Check line layer appears and disappears. | Browser: Travel option visible; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Separates transportation context.
L045 | Layer controls | Sea overlay toggle | Complete in code | Later | Moderate | Check marine lines appear and disappear. | Browser: Sea option visible; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Specialized marine context.
L046 | Layer controls | Cruise overlay toggle | Complete in code | Later | Moderate | Check itinerary lines appear and disappear. | Browser: Cruise option visible; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Specialized cruise context.
L047 | Layer controls | Foot overlay toggle | Complete in code | Important | Moderate | Check trails appear and disappear. | Browser: Foot option visible; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Helps walkers focus on paths.
L048 | Layer controls | Friend-tracking layer toggle | Partial | Critical | Hard | Confirm consent and per-trip behavior. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Shared location visibility is sensitive.
L049 | Layer controls | 2D/3D layer-panel toggle | Complete in code | Later | Moderate | Check tilt and reset. | Browser: 3D View option visible; Source: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Adds terrain perspective.
L050 | Layer controls | Layer-help descriptions | Complete in code | Important | Easy | Check text matches actual data. | Code only: LiveMapLayerControl.tsx | See acceptance / next action | UI extension | Sets expectations for each layer.
L051 | Layer controls | Sound toggle state | Partial | Later | Moderate | Verify any audible behavior and persistence. | Code only: LiveMapRightControls.tsx | See acceptance / next action | UI extension | UI state alone should be clear.
L052 | Layer controls | Notification toggle state | Partial | Later | Moderate | Verify actual notification behavior. | Code only: LiveMapRightControls.tsx | See acceptance / next action | UI extension | Avoids implying alerts are enabled.
L053 | Discovery pins | Discovery pins switch on and off | Partial | Critical | Hard | Verify toggle and error recovery. | Code only: live-map-discovery-layer-session.ts | See acceptance / next action | Graphic | User control needs a functioning layer.
L054 | Discovery pins | Default six discovery categories | Complete in code | Important | Easy | Confirm defaults on a fresh session. | Browser: Six categories selected in category panel; Source: live-map-discovery-categories.ts | See acceptance / next action | Graphic | Provides useful initial exploration.
L055 | Discovery pins | Per-category checkbox state | Complete in code | Important | Moderate | Toggle each category and verify pins. | Browser: 15 category checkboxes visible; Source: LiveDiscoveryCategoryPanel.tsx | See acceptance / next action | Graphic | Allows targeted discovery.
L056 | Discovery pins | Select-all category action | Complete in code | Important | Easy | Confirm every selectable category becomes active. | Browser: Select all button visible; Source: LiveDiscoveryCategoryPanel.tsx | See acceptance / next action | Graphic | Reduces repeated taps.
L057 | Discovery pins | Clear category selection | Partial | Important | Moderate | Confirm zero-selection behavior and map update. | Browser: Clear button visible; Source: LiveDiscoveryCategoryPanel.tsx | See acceptance / next action | Graphic | Clear must mean no pins rather than defaults.
L058 | Discovery pins | Category selection session persistence | Complete in code | Important | Moderate | Reload same session then start a new one. | Code only: live-map-discovery-categories.ts | See acceptance / next action | Graphic | User choices should behave predictably.
L059 | Discovery pins | Discovery viewport bounds request | Partial | Critical | Hard | Pan and verify the new bounding box fetches. | Code only: live-map-discovery-layer-bbox.ts | See acceptance / next action | Graphic | Pins must correspond to current map area.
L060 | Discovery pins | Discovery minimum zoom gate | Complete in code | Important | Moderate | Check precise zoom threshold and guidance. | Code only: live-map-discovery-layer-session.ts | See acceptance / next action | Graphic | Avoids overbroad queries and confusion.
L061 | Discovery pins | Discovery result count notice | Partial | Important | Moderate | Compare toast count to rendered pins. | Code only: LivePageClient.tsx | See acceptance / next action | Graphic | Counts must reflect actual results.
L062 | Discovery pins | Discovery fetch failure message | Partial | Critical | Moderate | Offer retry and distinguish failure from zero results. | Browser: Layer unavailable · try again in menu; Source: LivePageClient.tsx | See acceptance / next action | Graphic | Current layer failed in the sampled session.
L063 | Discovery pins | Discovery no-place state | Partial | Important | Moderate | Test sparse viewport with successful response. | Code only: LivePageClient.tsx | See acceptance / next action | Graphic | An empty map must be explained.
L064 | Discovery pins | Teal point symbol rendering | Partial | Important | Hard | Verify a successful payload visually. | Code only: live-map-discovery-layer-sync.ts | See acceptance / next action | Graphic | Pins are the output of discovery.
L065 | Discovery pins | Cluster bubble count | Partial | Important | Hard | Confirm count equals underlying places. | Code only: live-map-discovery-layer-sync.ts | See acceptance / next action | Graphic | A wrong count misstates coverage.
L066 | Discovery pins | Cluster tap zoom-to-expand | Partial | Important | Hard | Tap cluster through split levels. | Code only: live-map-discovery-layer-sync.ts | See acceptance / next action | Graphic | Dense areas need inspectable results.
L067 | Discovery pins | Discovery pin opens place selection | Partial | Critical | Hard | Tap a returned pin and verify exact place. | Code only: LivePageClient.tsx | See acceptance / next action | Graphic | Discovery has value only if places can be opened.
L068 | Discovery pins | Capital-level filter by zoom | Complete in code | Later | Moderate | Check national through local tier transitions. | Code only: live-capital-level.ts | See acceptance / next action | Graphic | Avoids showing every capital at once.
L069 | Overlay graphics | Saved pin glyph | Complete in code | Important | Moderate | Confirm saved pin differs from search pin. | Code only: live-saved-places-layer-sync.ts | See acceptance / next action | Graphic | Users need recognizable saved locations.
L070 | Overlay graphics | Saved pin click opens stored record | Partial | Important | Moderate | Select after reload and verify ID. | Code only: LivePageClient.tsx | See acceptance / next action | Graphic | Closes the save-and-revisit loop.
L071 | Overlay graphics | Report point glyph | Partial | Important | Moderate | Verify displayed reports at known test coordinates. | Code only: live-place-reports-sync.ts | See acceptance / next action | Graphic | Makes community observations discoverable.
L072 | Overlay graphics | Report marker fades at expiry | Partial | Important | Moderate | Test two-hour boundary and refresh. | Code only: live-place-reports-sync.ts | See acceptance / next action | Graphic | Old reports should disappear.
L073 | Overlay graphics | Travel highways overlay | Complete in code | Later | Hard | Check selected style and zoom visibility. | Code only: live-travel-layer-sync.ts | See acceptance / next action | Graphic | Useful high-level movement context.
L074 | Overlay graphics | Travel railway overlay | Complete in code | Later | Hard | Check rail depiction does not imply timetable. | Code only: live-travel-layer-vector.ts | See acceptance / next action | Graphic | Useful transit context.
L075 | Overlay graphics | Sea lane lines | Complete in code | Later | Hard | Verify static route geometry. | Code only: live-sea-routes-sync.ts | See acceptance / next action | Graphic | Specialized marine overview.
L076 | Overlay graphics | Ferry line layer | Complete in code | Later | Hard | Check source and visibility at relevant coasts. | Code only: live-sea-routes-sync.ts | See acceptance / next action | Graphic | Adds local crossing context.
L077 | Overlay graphics | Cruise itinerary lines | Complete in code | Later | Hard | Label static itinerary versus live service. | Code only: live-sea-routes-sync.ts | See acceptance / next action | Graphic | Avoids implying an operating cruise.
L078 | Overlay graphics | Footpath line layer | Complete in code | Important | Hard | Inspect trails in a known mapped area. | Code only: live-foot-routes-sync.ts | See acceptance / next action | Graphic | Supports walk and trek planning.
L079 | Overlay graphics | Friend avatar marker | Partial | Critical | Hard | Verify correct member identity in a real trip. | Code only: live-friend-layer-sync.ts | See acceptance / next action | Graphic | Wrong identity creates coordination risk.
L080 | Overlay graphics | Friend heading marker | Partial | Important | Hard | Compare heading against device movement. | Code only: live-friend-layer-sync.ts | See acceptance / next action | Graphic | Direction can help group meetings.
L081 | Overlay graphics | Friend stale-location appearance | Partial | Critical | Hard | Disconnect a device and inspect marker state. | Code only: live-friend-layer-sync.ts | See acceptance / next action | Graphic | Old positions must not look live.
L082 | Overlay graphics | Convoy vehicle marker | Partial | Important | Hard | Check vehicle-to-offer linkage in two clients. | Code only: live-convoy-pins-sync.ts | See acceptance / next action | Graphic | Makes seat offers locatable.
L083 | Overlay graphics | Pickup marker | Partial | Important | Hard | Check pickup links to correct vehicle. | Code only: live-convoy-pins-sync.ts | See acceptance / next action | Graphic | Prevents meeting at wrong point.
L084 | Overlay graphics | Vote option marker | Partial | Important | Hard | Check each pin matches a poll option. | Code only: live-vote-pins-sync.ts | See acceptance / next action | Graphic | Connects votes to places.
L085 | Search input | Search field focus and input | Complete in code | Critical | Easy | Check typing and accessible name. | Browser: Coffee nearby was selected from suggestions; Source: LivePageClient.tsx | See acceptance / next action | Feature | Starts the main discovery flow.
L086 | Search input | Search request debounce | Complete in code | Important | Moderate | Check one request per settled query. | Code only: live-geocoding.ts | See acceptance / next action | Feature | Limits noisy lookups.
L087 | Search input | Minimum-query threshold | Complete in code | Important | Easy | Check one-character and two-character behavior. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Avoids low-quality broad results.
L088 | Search input | Primary place autocomplete | Partial | Critical | Hard | Test city and venue queries across regions. | Code only: live-geocoding.ts | See acceptance / next action | Feature | Finding destinations is core.
L089 | Search input | Forward-geocoding fallback | Partial | Critical | Hard | Simulate unavailable primary search. | Code only: live-geocoding.ts | See acceptance / next action | Feature | Search needs graceful recovery.
L090 | Search input | Map-label search merge | Partial | Important | Hard | Check dedupe and ranking of tile labels. | Code only: live-search-merge.ts | See acceptance / next action | Feature | Adds locally visible places.
L091 | Search input | Suggestion dropdown open/close | Complete in code | Important | Moderate | Test focus, click-away and Escape. | Browser: Suggestions dropdown opened; Source: LivePageClient.tsx | See acceptance / next action | Feature | Suggestions should not trap input.
L092 | Search input | Recent-place suggestion | Complete in code | Important | Moderate | Select a previously visited place. | Code only: live-recent-searches.ts | See acceptance / next action | Feature | Speeds repeat visits.
L093 | Search input | Recent-category suggestion | Complete in code | Important | Moderate | Select a previous category query. | Browser: Coffee nearby recent item opened; Source: live-recent-searches.ts | See acceptance / next action | Feature | Speeds repeated nearby searches.
L094 | Search input | Recent dropped-pin suggestion | Complete in code | Later | Moderate | Reopen an exact dropped point. | Code only: live-recent-searches.ts | See acceptance / next action | Feature | Useful repeat map exploration.
L095 | Search input | Recent-search clear | Complete in code | Important | Easy | Clear and reload list. | Code only: live-recent-searches.ts | See acceptance / next action | Feature | Gives users control of history.
L096 | Search input | Per-account recent-search key | Complete in code | Important | Moderate | Switch accounts and check isolation. | Code only: live-recent-searches.ts | See acceptance / next action | Feature | Prevents mixed personal histories.
L097 | Search input | Instant suggestion filtering | Complete in code | Important | Moderate | Check keyword match and ordering. | Code only: live-search-suggestions.ts | See acceptance / next action | Feature | Improves search speed.
L098 | Search input | Search-loading indicator | Partial | Critical | Moderate | Check it clears when results settle. | Browser: Searching visible before results; lingered briefly; Source: LivePageClient.tsx | See acceptance / next action | Feature | Prevents stale loading claims.
L099 | Search input | Search zero-result message | Partial | Critical | Moderate | Test valid query with no nearby results. | Code only: LiveNearbyList.tsx | See acceptance / next action | Feature | Users need a true empty state.
L100 | Search input | Search request race cancellation | Partial | Critical | Hard | Issue fast changing queries and compare results. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Old results must not replace a new search.
L101 | Nearby results | Nearby heading reflects category | Complete in code | Important | Easy | Check coffee and other categories. | Browser: Coffee nearby heading rendered; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Explains what the list contains.
L102 | Nearby results | Nearby total count | Complete in code | Critical | Easy | Compare count with unique rows. | Browser: 12 found in Chicago sample; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Prevents overstated results.
L103 | Nearby results | Distance-sorted result order | Complete in code | Critical | Moderate | Recompute sample distances from anchor. | Browser: Results displayed from 0.3 to 1.0 mi; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Nearest should mean nearest.
L104 | Nearby results | Distance unit display | Complete in code | Important | Easy | Check miles/kilometers locale behavior. | Browser: Nearby rows displayed mi; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Distances must be interpretable.
L105 | Nearby results | Result rank badge | Complete in code | Important | Easy | Compare rank to matching map pin. | Browser: Ranks 1–12 displayed; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Links list and map.
L106 | Nearby results | Result category subtitle | Complete in code | Important | Moderate | Check type against source tags. | Browser: Sample rows displayed Cafe; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Avoids mislabeling a venue.
L107 | Nearby results | Result address subtitle | Partial | Critical | Moderate | Check address provenance and missing cases. | Browser: Sample rows displayed Chicago addresses; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Supports choosing the right branch.
L108 | Nearby results | Result click selects destination | Complete in code | Critical | Moderate | Open result and inspect route target. | Browser: Pan Artesanal click produced route summary; Source: LiveNearbyList.tsx | See acceptance / next action | UI extension | Completes nearby-to-route flow.
L109 | Nearby results | Nearby close button | Complete in code | Important | Easy | Confirm map remains usable after close. | Code only: LiveNearbyList.tsx | See acceptance / next action | UI extension | Restores browsing space.
L110 | Nearby results | Nearby result pin glyph | Complete in code | Important | Moderate | Check map/list rank and icon match. | Browser: 12 numbered coffee map pins rendered; Source: live-marker-elements.ts | See acceptance / next action | UI extension | Avoids ambiguity on the map.
L111 | Nearby results | Nearby result limit by screen | Complete in code | Later | Moderate | Compare phone and desktop limit. | Code only: live-search-categories.ts | See acceptance / next action | UI extension | Balances density and coverage.
L112 | Nearby results | Nearby search anchor label | Partial | Critical | Moderate | Distinguish map area from GPS area. | Code only: LiveNearbyList.tsx | See acceptance / next action | UI extension | Users need to know what nearby means.
L113 | Map pick | POI-first map click selection | Partial | Critical | Hard | Tap adjacent road and POI features. | Code only: live-map-poi-pick.ts | See acceptance / next action | Feature | Prevents wrong destination selection.
L114 | Map pick | Reverse geocode bare-map tap | Partial | Critical | Hard | Tap unmapped place and confirm coordinate. | Code only: live-geocoding.ts | See acceptance / next action | Feature | Makes arbitrary points useful.
L115 | Map pick | Double-click map location action | Complete in code | Important | Moderate | Check exact point and zoom interaction. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Provides a quick map action.
L116 | Map pick | Long-press map location action | Complete in code | Important | Moderate | Test phone press without accidental drag. | Code only: live-map-long-press-bind.ts | See acceptance / next action | Feature | Gives touch users a context menu.
L117 | Map pick | Dropped-pin coordinate label | Complete in code | Important | Easy | Compare shown values with tap point. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Allows exact location verification.
L118 | Map pick | Set map point as origin | Complete in code | Critical | Moderate | Confirm route recalculates from chosen point. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Users must control start position.
L119 | Map pick | Set map point as destination | Complete in code | Critical | Moderate | Confirm selected marker and route update. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Makes arbitrary destinations routable.
L120 | Map pick | Add map point as stop | Partial | Important | Hard | Confirm route geometry includes new stop. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Supports multi-stop journeys.
L121 | Map pick | Copy map coordinates | Complete in code | Important | Easy | Paste copied value and compare. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Makes exact places shareable.
L122 | Map pick | Save map point locally | Partial | Important | Moderate | Reload and reopen point. | Code only: LiveMapLocationSheet.tsx | See acceptance / next action | Feature | Makes picked locations reusable.
L123 | Map pick | Tap-geocode result cache | Complete in code | Later | Moderate | Repeat tap and verify stale controls. | Code only: live-tap-geocode-cache.ts | See acceptance / next action | Feature | Reduces repeat lookup delay.
L124 | Map pick | Open-water rejection state | Partial | Critical | Hard | Tap ocean at multiple zooms. | Code only: live-open-water-place.ts | See acceptance / next action | Feature | Avoids invented land destinations.
L125 | Place identity | OSM place name display | Complete in code | Critical | Moderate | Compare map feature name and panel. | Code only: live-place-display.ts | See acceptance / next action | Feature | The destination name must match the selected place.
L126 | Place identity | Category label normalization | Partial | Important | Moderate | Compare enriched and preview category. | Code only: live-place-category-label.ts | See acceptance / next action | Feature | Current sampled category/title differed.
L127 | Place identity | Street address assembly | Partial | Critical | Hard | Check complete, partial and absent tags. | Code only: live-osm-address.ts | See acceptance / next action | Feature | Users need a reliable address.
L128 | Place identity | City field from reverse geocode | Partial | Important | Hard | Check city versus neighborhood on samples. | Browser: Chicago shown in Info; Source: live-place-admin-hierarchy.ts | See acceptance / next action | Feature | Correct locality avoids wrong-branch selection.
L129 | Place identity | State/province field | Partial | Important | Moderate | Check administrative level by country. | Browser: Illinois shown in Info; Source: live-place-admin-hierarchy.ts | See acceptance / next action | Feature | Provides regional context.
L130 | Place identity | Country field | Partial | Important | Moderate | Check cross-border samples. | Browser: United States shown in Info; Source: live-place-admin-hierarchy.ts | See acceptance / next action | Feature | Avoids travel planning in wrong country.
L131 | Place identity | Coordinates in Info tab | Complete in code | Important | Easy | Compare with selected pin. | Code only: PlacePanelLiveChrome.tsx | See acceptance / next action | Feature | Supports exact position checks.
L132 | Place identity | Opening-hours field | Partial | Critical | Hard | Keep unknown when no source hours exist. | Code only: PlacePanelLiveChrome.tsx | See acceptance / next action | Feature | Hours influence whether a visit is practical.
L133 | Place identity | Open-status qualifier | Partial | Critical | Hard | Compute only from reliable hours/time zone. | Code only: PlacePanelLiveChrome.tsx | See acceptance / next action | Feature | A stale open claim can mislead travel.
L134 | Place identity | Place media lookup | Partial | Important | Hard | Verify media belongs to exact venue. | Code only: live-place-media.ts | See acceptance / next action | Feature | Wrong photos undermine trust.
L135 | Place identity | Photo-free fallback | Complete in code | Important | Easy | Show empty media state honestly. | Browser: No Rovvy photos yet appeared; Source: PlacePanel.tsx | See acceptance / next action | Feature | Avoids unrelated placeholder photos.
L136 | Place identity | Wikidata or spine identity match | Partial | Critical | Very hard | Check exact ID and nearest fallback for close POIs. | Code only: live-place-spine.ts | See acceptance / next action | Feature | Wrong record enrichment corrupts details.
L137 | Place identity | Nearest-spine distance cap | Partial | Critical | Hard | Test multiple spine rows within radius. | Code only: LivePlacePanelHost.tsx | See acceptance / next action | Feature | A nearest match may be the wrong business.
L138 | Place identity | Enriched title reconciliation | Partial | Critical | Hard | Confirm name/category/address agree after merge. | Browser: Title changed to Pan Artesanal Bakery while category remained Cafe; Source: LivePlacePanelHost.tsx | See acceptance / next action | Feature | The sampled title changed after enrichment.
L139 | Place identity | Local script and transliterated name | Partial | Important | Hard | Check multilingual names and user locale. | Code only: live-place-name-i18n.ts | See acceptance / next action | Feature | Improves place recognition abroad.
L140 | Place identity | Place trust badge | Partial | Important | Hard | Verify badge derives from source and freshness. | Code only: LiveDataTrustBadge.tsx | See acceptance / next action | Feature | Trust labels should have evidence.
L141 | Place panel UI | Place sheet drag handle | Complete in code | Important | Moderate | Test drag with pointer and touch. | Browser: Splitter Drag to expand visible; Source: PlacePanel.tsx | See acceptance / next action | UI extension | Lets users reveal more detail.
L142 | Place panel UI | Place sheet close action | Complete in code | Critical | Easy | Close by button and restore map focus. | Browser: Close returned to route summary; Source: PlacePanel.tsx | See acceptance / next action | UI extension | Users need to return to map.
L143 | Place panel UI | Place sheet focus management | Partial | Important | Moderate | Test tab order and focus restoration. | Code only: use-place-panel-focus.ts | See acceptance / next action | UI extension | Keyboard users need a predictable path.
L144 | Place panel UI | Place sheet responsive width | Partial | Critical | Hard | Test narrow phone through desktop sizes. | Code only: LivePlacePanelHost.tsx | See acceptance / next action | UI extension | Information must stay readable.
L145 | Place panel UI | Guide tab selection | Complete in code | Important | Easy | Switch from other tabs and retain content. | Browser: Guide content opened; Source: PlacePanelLiveChrome.tsx | See acceptance / next action | UI extension | Guide is the primary action surface.
L146 | Place panel UI | About tab selection | Complete in code | Important | Easy | Switch and inspect Wikipedia state. | Browser: About showed exact-pin no-match Wikipedia state; Source: PlacePanelLiveChrome.tsx | See acceptance / next action | UI extension | Background context has a distinct home.
L147 | Place panel UI | Info tab selection | Complete in code | Critical | Easy | Switch and inspect factual fields. | Browser: Info showed locality and category; Source: PlacePanelLiveChrome.tsx | See acceptance / next action | UI extension | Users need direct venue facts.
L148 | Place panel UI | Wikipedia exact-match no-result state | Complete in code | Important | Moderate | Verify no unrelated article appears. | Browser: No exact Wikipedia article for Pan Artesanal; Source: PlaceWikiAboutSection.tsx | See acceptance / next action | UI extension | Avoids false place biographies.
L149 | Place panel UI | Wikipedia summary expansion | Complete in code | Later | Moderate | Check expand/collapse and citation. | Code only: PlaceWikiAboutSection.tsx | See acceptance / next action | UI extension | Long descriptions should be manageable.
L150 | Place panel UI | Place photo grid | Partial | Later | Moderate | Verify layout with 1, 2 and many photos. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Improves visual assessment.
L151 | Place panel UI | Photo lightbox open | Complete in code | Later | Moderate | Open a populated photo record. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Lets users inspect venue imagery.
L152 | Place panel UI | Photo lightbox close | Complete in code | Later | Easy | Test button and keyboard close. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Prevents trapped overlay.
L153 | Place panel UI | Directions action in place panel | Partial | Critical | Hard | Confirm route and auth lifecycle. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Connects place details to travel.
L154 | Place panel UI | Add-to-plan action in place panel | Partial | Important | Hard | Confirm persisted plan and state cue. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Makes selected places actionable.
L155 | Place panel UI | Ask-group action in place panel | Partial | Important | Hard | Confirm real group context or label limitation. | Code only: PlacePanel.tsx | See acceptance / next action | UI extension | Group intent should not imply delivery.
L156 | Place panel UI | Group attendance placeholder | Pending | Later | Hard | Replace copy with real attendance if enabled. | Code only: PlacePanelLiveChrome.tsx | See acceptance / next action | UI extension | Avoids invented social proof.
L157 | Route preview detail | Fresh GPS origin candidate | Partial | Critical | Hard | Verify freshness threshold before selection. | Code only: live-route-origin.ts | See acceptance / next action | Feature | A stale origin yields a wrong route.
L158 | Route preview detail | User-picked origin candidate | Complete in code | Critical | Moderate | Ensure user choice survives GPS updates. | Code only: live-route-origin.ts | See acceptance / next action | Feature | Explicit starting point takes priority.
L159 | Route preview detail | Map-center origin fallback | Partial | Critical | Moderate | Label map-center fallback visibly. | Code only: live-route-origin.ts | See acceptance / next action | Feature | Silent fallback can mislead route distance.
L160 | Route preview detail | Origin-search option | Complete in code | Important | Hard | Select searched origin and recalculate. | Code only: LiveRouteOriginSetup.tsx | See acceptance / next action | Feature | Useful when planning from elsewhere.
L161 | Route preview detail | Origin map-pick mode | Complete in code | Important | Moderate | Pick start without changing destination. | Code only: LiveRouteOriginSetup.tsx | See acceptance / next action | Feature | Supports remote route planning.
L162 | Route preview detail | Route loading state | Partial | Critical | Moderate | Keep old route from appearing current. | Code only: LiveRouteSummaryBar.tsx | See acceptance / next action | Feature | Loading must distinguish stale geometry.
L163 | Route preview detail | Route ready state | Complete in code | Critical | Moderate | Compare provider route and displayed summary. | Browser: Drive route ready and 1 min summary rendered; Source: LiveRouteSummaryBar.tsx | See acceptance / next action | Feature | Enables informed start.
L164 | Route preview detail | Route error retry | Partial | Critical | Moderate | Retry after simulated provider failure. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Travel must recover from transient errors.
L165 | Route preview detail | Route alternative selection | Partial | Important | Hard | Compare selected route geometry and ETA. | Code only: SoloRoutePreviewPanel.tsx | See acceptance / next action | Feature | Alternatives need real consequences.
L166 | Route preview detail | Toll versus no-toll route choice | Partial | Important | Hard | Verify provider labels and route switching. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Cost preferences affect decisions.
L167 | Route preview detail | Route distance format | Partial | Critical | Moderate | Check unit conversion and rounding. | Code only: live-types.ts | See acceptance / next action | Feature | Wrong numbers misstate trip length.
L168 | Route preview detail | Route duration format | Partial | Critical | Moderate | Compare with backend duration. | Code only: live-types.ts | See acceptance / next action | Feature | ETA depends on accurate duration.
L169 | Route preview detail | Route line casing | Complete in code | Important | Moderate | Check visibility against each base layer. | Code only: live-route-style.ts | See acceptance / next action | Feature | Route must stand out on all styles.
L170 | Route preview detail | Route direction arrows | Complete in code | Important | Moderate | Check arrows follow geometry. | Code only: live-route-style.ts | See acceptance / next action | Feature | Clarifies travel direction.
L171 | Route preview detail | Last-mile dashed walk segment | Partial | Important | Hard | Verify segment begins at road end. | Code only: live-routing.ts | See acceptance / next action | Feature | Distinguishes driving from final walk.
L172 | Route preview detail | Unroutable drive blocking | Partial | Critical | Hard | Test disconnected land and water cases. | Code only: live-route-validation.ts | See acceptance / next action | Feature | Avoids dangerous false routes.
L173 | Route preview detail | Far-distance route intelligence | Partial | Important | Very hard | Check when local route hands off. | Code only: route-intelligence.ts | See acceptance / next action | Feature | Long journeys need different travel modes.
L174 | Route preview detail | Travel planning handoff | Partial | Important | Hard | Verify destination and origin survive navigation. | Code only: live-travel-handoff.ts | See acceptance / next action | Feature | Prevents re-entering trip details.
L175 | Navigation detail | Navigation camera follow | Partial | Critical | Hard | Test moving GPS and manual-pan escape. | Code only: LiveMapComponent.tsx | See acceptance / next action | Feature | Map view should track actual travel.
L176 | Navigation detail | Navigation bearing adjustment | Partial | Important | Hard | Compare heading with GPS course. | Code only: live-route-bearing.ts | See acceptance / next action | Feature | Keeps forward direction intuitive.
L177 | Navigation detail | Navigation 3D pitch | Complete in code | Later | Moderate | Check pitch on start and reset on end. | Browser: Start directions entered Solo Live view; Source: LiveMapComponent.tsx | See acceptance / next action | Feature | Enhances view without trapping users.
L178 | Navigation detail | Turn instruction text | Partial | Critical | Very hard | Advance along route and check each step. | Browser: Continue toward Pan Artesanal shown; Source: live-navigation-maneuver.ts | See acceptance / next action | Feature | Turn text must reflect current maneuver.
L179 | Navigation detail | Turn distance label | Partial | Critical | Very hard | Compare with remaining distance to next turn. | Browser: 0.1 MI shown in turn banner; Source: live-navigation-maneuver.ts | See acceptance / next action | Feature | Wrong distances can cause missed turns.
L180 | Navigation detail | Generated lane-hint arrows | Partial | Critical | Hard | Hide unless backed by lane-level data. | Browser: Four arrows shown in Solo overlay; Source: live-navigation-maneuver.ts | See acceptance / next action | Feature | Current arrows are generated by turn kind.
L181 | Navigation detail | Remaining route distance | Partial | Critical | Very hard | Resolve sampled zero-left discrepancy. | Browser: 0 m LEFT shown beside nonzero turn distance; Source: SoloLiveNavigationOverlay.tsx | See acceptance / next action | Feature | Users rely on trip progress.
L182 | Navigation detail | Arrival clock time | Partial | Critical | Hard | Use route duration and current time zone. | Browser: Clock time and 1 min ETA shown; Source: SoloLiveNavigationOverlay.tsx | See acceptance / next action | Feature | Arrival time affects coordination.
L183 | Navigation detail | Speed unit label | Complete in code | Important | Easy | Check MPH versus unit preference. | Code only: SoloLiveNavigationOverlay.tsx | See acceptance / next action | Feature | Telemetry requires clear units.
L184 | Navigation detail | Unknown speed state | Complete in code | Important | Easy | Distinguish unavailable from zero. | Browser: Dash MPH shown without GPS speed; Source: SoloLiveNavigationOverlay.tsx | See acceptance / next action | Feature | Avoids misleading speed display.
L185 | Navigation detail | Parking save action | Pending | Important | Moderate | Store precise parking point before saved toast. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | A false save can strand a user.
L186 | Navigation detail | Share trip action | Pending | Important | Hard | Implement a permission-aware share outcome. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Current action only says coming soon.
L187 | Navigation detail | Add stop from navigation | Partial | Important | Hard | Recalculate active route after selection. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Live detours require a real update.
L188 | Navigation detail | End navigation action | Complete in code | Critical | Moderate | Verify camera and stage reset. | Browser: END returned to destination state; Source: LivePageClient.tsx | See acceptance / next action | Feature | Users need to stop tracking.
L189 | Navigation detail | Route overview action | Partial | Important | Moderate | Restore route bounds after navigation view. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Helps understand remaining journey.
L190 | GPS states | GPS idle state | Complete in code | Important | Easy | Verify no live claim before permission. | Code only: live-gps.ts | See acceptance / next action | Feature | Users should know tracking status.
L191 | GPS states | GPS request state | Complete in code | Important | Easy | Show waiting feedback during permission flow. | Code only: live-gps.ts | See acceptance / next action | Feature | Reduces uncertainty.
L192 | GPS states | GPS active state | Partial | Critical | Hard | Verify fresh fixes from device. | Code only: live-gps.ts | See acceptance / next action | Feature | Navigation relies on real position.
L193 | GPS states | GPS approximate state | Partial | Critical | Hard | Show accuracy warning and limit claims. | Code only: live-gps.ts | See acceptance / next action | Feature | Approximate data should not appear precise.
L194 | GPS states | GPS denied state | Partial | Critical | Moderate | Offer manual-origin path after denial. | Code only: live-gps.ts | See acceptance / next action | Feature | Users can still plan a route.
L195 | GPS states | GPS unavailable state | Partial | Critical | Moderate | Test unsupported device and provider error. | Code only: live-gps.ts | See acceptance / next action | Feature | Failure should be actionable.
L196 | GPS states | GPS stale state | Partial | Critical | Hard | Reacquire or mark location old. | Code only: live-gps.ts | See acceptance / next action | Feature | A stale fix can misdirect users.
L197 | GPS states | GPS browse pulse marker | Partial | Important | Hard | Verify correct location and appearance. | Code only: live-gps-marker.ts | See acceptance / next action | Feature | Shows current area anchor.
L198 | GPS states | GPS navigating heading cone | Partial | Important | Hard | Compare cone with actual movement. | Code only: live-gps-marker.ts | See acceptance / next action | Feature | Makes orientation useful.
L199 | GPS states | GPS locate-me recenter | Partial | Critical | Hard | Test permission and recenter after pan. | Code only: LiveMapRightControls.tsx | See acceptance / next action | Feature | Users need to find themselves.
L200 | GPS states | Use-map-area fallback | Complete in code | Important | Moderate | Check manual area when GPS fails. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Keeps discovery accessible.
L201 | GPS states | GPS helper dismissal | Complete in code | Later | Easy | Confirm dismissal does not claim GPS active. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Keeps helper unobtrusive.
L202 | Group vote detail | Trip-linked poll creation | Partial | Important | Hard | Create with authenticated trip and two users. | Code only: live-group-vote-network.ts | Trip context + auth | Feature | Group choice must persist.
L203 | Group vote detail | Poll option addition from search | Partial | Important | Hard | Add a selected venue with correct coordinates. | Code only: LivePageClient.tsx | Trip context + auth | Feature | Lets groups compare real places.
L204 | Group vote detail | Poll option map pin | Partial | Important | Hard | Check option pin and text match. | Code only: live-vote-pins-sync.ts | Trip context + auth | Feature | Visualizes alternatives.
L205 | Group vote detail | Poll option count bar | Partial | Important | Moderate | Compare count with server ballots. | Code only: LiveGroupVotePanel.tsx | Trip context + auth | Feature | Vote graphics must be truthful.
L206 | Group vote detail | My-vote selected state | Partial | Important | Moderate | Reload after vote and check state. | Code only: LiveGroupVotePanel.tsx | Trip context + auth | Feature | Prevents duplicate or uncertain voting.
L207 | Group vote detail | Vote submission error state | Partial | Critical | Moderate | Simulate 401 and network failure. | Code only: use-live-group-vote.ts | Trip context + auth | Feature | Votes must not appear counted on error.
L208 | Group vote detail | Poll refresh interval | Complete in code | Important | Moderate | Verify 15-second refresh and cleanup. | Code only: use-live-group-vote.ts | Trip context + auth | Feature | Keeps shared totals current.
L209 | Group vote detail | Poll close or winner state | Partial | Important | Hard | Verify backend outcome and visible result. | Code only: LiveGroupVotePanel.tsx | Trip context + auth | Feature | Groups need a decision endpoint.
L210 | Group vote detail | Mock-poll fallback labeling | Partial | Critical | Moderate | Label non-trip demo clearly. | Code only: live-group-vote-mock.ts | Trip context + auth | Feature | Demo votes must not look shared.
L211 | Group vote detail | Quick action after vote | Partial | Important | Hard | Verify actions produce durable state. | Code only: LiveGroupVotePanel.tsx | Trip context + auth | Feature | Voting should lead to a real next step.
L212 | Convergence detail | Group session start API | Partial | Critical | Hard | Check permission and error response. | Code only: live-group-network.ts | Trip context + auth | Feature | Controls location sharing lifecycle.
L213 | Convergence detail | Firebase custom-token auth | Partial | Critical | Very hard | Verify token expiration and unauthorized access. | Code only: live-firebase-auth.ts | Trip context + auth | Feature | Protects shared location data.
L214 | Convergence detail | Trip member roster fetch | Partial | Important | Hard | Compare with authorized group membership. | Code only: live-group-network.ts | Trip context + auth | Feature | Avoids missing or extra participants.
L215 | Convergence detail | Live member location subscription | Partial | Critical | Very hard | Use two moving devices and reconnect. | Code only: live-group-location-sync.ts | Trip context + auth | Feature | Core group convergence signal.
L216 | Convergence detail | Member location publication | Partial | Critical | Very hard | Confirm permission and update frequency. | Code only: live-group-location-sync.ts | Trip context + auth | Feature | Shared positions must be current.
L217 | Convergence detail | Member ETA estimation | Partial | Critical | Hard | Compare estimates with route and GPS. | Code only: live-group-converge.ts | Trip context + auth | Feature | Waiting decisions depend on ETA.
L218 | Convergence detail | Member freshness pill | Partial | Critical | Moderate | Disconnect device and inspect age. | Code only: LiveGroupConvergePanel.tsx | Trip context + auth | Feature | Old locations must look old.
L219 | Convergence detail | Last-member-in callout | Partial | Important | Moderate | Check calculation from live roster. | Code only: LiveGroupConvergePanel.tsx | Trip context + auth | Feature | Helps group coordinate arrival.
L220 | Convergence detail | Arrival count banner | Partial | Important | Hard | Verify geofence and member count. | Code only: use-live-group-arrival.ts | Trip context + auth | Feature | Closing the night depends on arrivals.
L221 | Convergence detail | Convergence status notice | Partial | Important | Moderate | Match copy to actual session state. | Code only: LiveMapNoticeStack.tsx | Trip context + auth | Feature | Provides glanceable group status.
L222 | Convergence detail | Wayra notice dismissal | Complete in code | Later | Easy | Dismiss and verify state. | Code only: LiveGroupConvergePanel.tsx | Trip context + auth | Feature | Keeps map usable after notice.
L223 | Convergence detail | Mock friend fallback labeling | Partial | Critical | Moderate | Do not present demo people as live friends. | Code only: live-group-converge-mock.ts | Trip context + auth | Feature | False people locations are misleading.
L224 | Seat Share detail | Vehicle offer card | Partial | Important | Moderate | Compare title and offer ID. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Riders need to identify drivers.
L225 | Seat Share detail | Open-seat number | Partial | Critical | Hard | Verify concurrent joins update capacity. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Avoids overbooking.
L226 | Seat Share detail | Route summary on vehicle card | Partial | Important | Moderate | Compare with offer route. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Riders need destination compatibility.
L227 | Seat Share detail | Cost-per-head estimate | Partial | Critical | Hard | Show assumptions and actual currency. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Price claims affect decisions.
L228 | Seat Share detail | Pickup list per vehicle | Partial | Important | Hard | Check each pickup belongs to offer. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Prevents wrong pickup choice.
L229 | Seat Share detail | Join-seat transaction | Partial | Critical | Very hard | Race two users on one remaining seat. | Code only: live-convoy-sync.ts | Trip context + auth | Feature | Capacity must be enforced atomically.
L230 | Seat Share detail | Joined-driver state | Partial | Important | Hard | Reload and verify selected vehicle. | Code only: live-convoy-actions.ts | Trip context + auth | Feature | Users need reliable confirmation.
L231 | Seat Share detail | Add-pickup transaction | Partial | Important | Hard | Verify server confirmation and map pin. | Code only: live-convoy-sync.ts | Trip context + auth | Feature | Pickup must persist for group.
L232 | Seat Share detail | Broadcast own seats | Partial | Important | Hard | Wait for publish success before toast. | Code only: use-live-seat-share.ts | Trip context + auth | Feature | Do not claim an unseen offer exists.
L233 | Seat Share detail | Convoy subscription | Partial | Important | Very hard | Verify changes across two clients. | Code only: live-convoy-sync.ts | Trip context + auth | Feature | Offers need live updates.
L234 | Seat Share detail | Empty vehicles state | Complete in code | Important | Easy | Open an empty real trip. | Code only: LiveSeatSharePanel.tsx | Trip context + auth | Feature | Avoids mock vehicle leakage.
L235 | Seat Share detail | Mock convoy fallback labeling | Partial | Critical | Moderate | Label sample offers as demo. | Code only: live-seat-share-mock.ts | Trip context + auth | Feature | Users must not try to join fictional seats.
L236 | Settlement detail | Night-finished panel heading | Partial | Important | Easy | Check real destination and group status. | Code only: LiveNightFinishedPanel.tsx | See acceptance / next action | Feature | Anchors the closing workflow.
L237 | Settlement detail | Arrived versus member count | Partial | Critical | Hard | Compare live arrival records. | Code only: live-night-finished.ts | See acceptance / next action | Feature | False counts mislead the group.
L238 | Settlement detail | Expense total fetch | Partial | Critical | Hard | Compare returned expenses with total. | Code only: live-trip-expenses-network.ts | See acceptance / next action | Feature | Settlement depends on complete charges.
L239 | Settlement detail | Mixed-currency guard | Complete in code | Critical | Moderate | Verify mixed currencies do not sum. | Code only: live-night-finished.ts | See acceptance / next action | Feature | Prevents mathematically invalid total.
L240 | Settlement detail | Per-person split estimate | Partial | Critical | Hard | Check who is included and rounding. | Code only: live-night-finished.ts | See acceptance / next action | Feature | Cost allocation can affect people.
L241 | Settlement detail | Open split route | Partial | Important | Moderate | Carry correct trip ID to split page. | Code only: LiveNightFinishedPanel.tsx | See acceptance / next action | Feature | Avoids settling the wrong group.
L242 | Settlement detail | Mark-arrived update | Pending | Important | Hard | Persist the change before success toast. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Current copy asserts unsaved state.
L243 | Settlement detail | Late-member nudge | Pending | Important | Hard | Deliver nudge before sent toast. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Current copy asserts undelivered contact.
L244 | Settlement detail | Place report from settlement | Partial | Important | Moderate | Open correct place and location. | Code only: LiveNightFinishedPanel.tsx | See acceptance / next action | Feature | Connects end-of-night feedback.
L245 | Reports detail | Long-line report choice | Partial | Important | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Queue data is time sensitive.
L246 | Reports detail | Packed report choice | Partial | Important | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Crowding affects a visit.
L247 | Reports detail | Quiet report choice | Partial | Important | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Availability affects meet plans.
L248 | Reports detail | Price-changed report choice | Partial | Important | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Cost changes affect budgets.
L249 | Reports detail | Closed-early report choice | Partial | Critical | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Avoids a wasted trip.
L250 | Reports detail | No-parking report choice | Partial | Important | Moderate | Submit and verify source/time. | Browser: Choice visible in report modal; not submitted; Source: LiveReportModal.tsx | See acceptance / next action | Feature | Drive users may need another plan.
L251 | Reports detail | Report anonymous browse | Partial | Important | Moderate | Fetch without login and check privacy. | Code only: live-place-reports.ts | See acceptance / next action | Feature | Visitors need useful updates.
L252 | Reports detail | Report sign-in prompt | Complete in code | Important | Moderate | Attempt submission without credentials. | Code only: LiveReportModal.tsx | See acceptance / next action | Feature | Submission identity supports abuse control.
L253 | Reports detail | Report expiry after two hours | Partial | Critical | Hard | Verify boundary and clock skew. | Code only: live-place-report-types.ts | See acceptance / next action | Feature | Old reports should not look current.
L254 | Reports detail | Three-match confirmation threshold | Partial | Critical | Hard | Test independent users and duplicates. | Code only: live-place-report-types.ts | See acceptance / next action | Feature | Confirmation must be evidence based.
L255 | Reports detail | Report submission failure message | Pending | Critical | Moderate | Display non-auth failures visibly. | Code only: LiveReportModal.tsx | See acceptance / next action | Feature | Silent failure hides lost reports.
L256 | Saved-place detail | Local save from place panel | Partial | Important | Moderate | Reload and verify selected coordinates. | Code only: live-saved-places-store.ts | See acceptance / next action | Feature | Preserves trip ideas.
L257 | Saved-place detail | Local save from map pick | Partial | Important | Moderate | Reload and reopen dropped point. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Preserves arbitrary locations.
L258 | Saved-place detail | Account add-location sync | Partial | Important | Hard | Verify authenticated API and error feedback. | Code only: live-preview-actions.ts | See acceptance / next action | Feature | Connects browser and account plans.
L259 | Saved-place detail | Saved-place label edit | Partial | Important | Moderate | Edit label and reload. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Makes personal pins recognizable.
L260 | Saved-place detail | Saved-place photo attachment | Partial | Later | Hard | Attach and reopen a photo. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Adds personal context.
L261 | Saved-place detail | Saved-place audio attachment | Partial | Later | Hard | Attach and replay audio. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Optional richer note.
L262 | Saved-place detail | Saved-place file attachment | Partial | Later | Hard | Attach and reopen file. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Optional trip reference.
L263 | Saved-place detail | Saved-place attachment removal | Partial | Later | Moderate | Remove attachment and reload. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Lets users correct notes.
L264 | Saved-place detail | Saved-place deletion | Partial | Important | Moderate | Delete and confirm marker disappears. | Code only: SavedPlacePanel.tsx | See acceptance / next action | Feature | Users need control of stored pins.
L265 | Saved-place detail | Trip saved-location merge | Partial | Important | Hard | Compare trip places with local saves. | Code only: LivePageClient.tsx | See acceptance / next action | Feature | Group and personal pins should coexist.
L266 | Wayra detail | Wayra launcher drag position | Complete in code | Later | Moderate | Drag and confirm no control overlap. | Code only: AIAssistantSidecar.tsx | See acceptance / next action | UI extension | Assistant should not cover map actions.
L267 | Wayra detail | Wayra launcher open/close | Complete in code | Important | Easy | Open and close without losing place. | Code only: AIAssistantSidecar.tsx | See acceptance / next action | UI extension | Keeps contextual help accessible.
L268 | Wayra detail | Place context sent to Wayra | Partial | Important | Hard | Inspect exact selected place in assistant. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | Wrong context produces irrelevant advice.
L269 | Wayra detail | Route context sent to Wayra | Partial | Important | Hard | Inspect route mode and destination. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | Advice should match trip.
L270 | Wayra detail | GPS-only context sent to Wayra | Partial | Important | Hard | Verify no precise position leak beyond intended use. | Code only: live-location-context.ts | See acceptance / next action | UI extension | Location advice depends on consent.
L271 | Wayra detail | Wayra map-focus command | Partial | Important | Hard | Ask assistant to focus a place. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | Connects chat back to map.
L272 | Wayra detail | Clear Wayra context on place change | Partial | Critical | Moderate | Switch destination and inspect context. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | Prevents answer about previous place.
L273 | Wayra detail | AI place explanation loading | Partial | Later | Moderate | Check unavailable API behavior. | Code only: live-rovi.ts | See acceptance / next action | UI extension | Generated context should fail clearly.
L274 | Wayra detail | AI suggestion chips | Partial | Later | Moderate | Check suggestions use current route. | Code only: LiveAiSuggestionsBlock.tsx | See acceptance / next action | UI extension | Prompts should be relevant.
L275 | Wayra detail | Route failure handoff to Wayra | Partial | Later | Hard | Trigger route error and inspect prompt. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | Offers guidance when routing fails.
L276 | Workflow setup | Trip setup dock icon | Complete in code | Critical | Easy | Open setup and confirm selection. | Browser: Opened setup panel; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Main entry to planning.
L277 | Workflow setup | Category-filter dock icon | Complete in code | Important | Easy | Open filters with map state intact. | Browser: Opened category panel; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Makes category controls discoverable.
L278 | Workflow setup | Nearby-results dock icon | Partial | Important | Easy | Show actual result prerequisite. | Browser: Opened after category search; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Users should understand when list exists.
L279 | Workflow setup | Place-details dock icon | Partial | Important | Easy | Open currently selected place. | Code only: LiveDockRail.tsx | See acceptance / next action | UI extension | Returns to venue facts.
L280 | Workflow setup | Vote dock icon | Partial | Important | Moderate | Gate on a real or clearly marked mock poll. | Browser: Prerequisite toast shown; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Avoids empty vote pane.
L281 | Workflow setup | Convergence dock icon | Partial | Important | Moderate | Gate on active group session. | Code only: LiveDockRail.tsx | See acceptance / next action | UI extension | Avoids implying tracking is active.
L282 | Workflow setup | Navigation dock icon | Pending | Important | Hard | Connect to actual navigation status. | Code only: live-dock-stages.ts | See acceptance / next action | UI extension | Current rail stage is disabled.
L283 | Workflow setup | Seat Share dock icon | Partial | Important | Moderate | Gate on seat-share workflow. | Browser: Prerequisite toast shown; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Avoids unrelated vehicle cards.
L284 | Workflow setup | Notifications dock icon | Pending | Later | Hard | Implement inbox before enabling. | Browser: Coming in Group Live phase toast shown; Source: live-dock-stages.ts | See acceptance / next action | UI extension | Current rail stage is disabled.
L285 | Workflow setup | Settle-up dock icon | Partial | Important | Moderate | Gate on finished group night. | Code only: LiveDockRail.tsx | See acceptance / next action | UI extension | Keeps finance action contextual.
L286 | Workflow setup | Drive mode selection | Partial | Critical | Hard | Route with drive profile. | Browser: Drive visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Driving restrictions affect safety.
L287 | Workflow setup | Bike mode selection | Partial | Critical | Hard | Route with bike profile. | Browser: Bike visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Cycling needs suitable roads.
L288 | Workflow setup | Trek mode selection | Partial | Important | Hard | Route with trek profile. | Browser: Trek visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Trail suitability differs from streets.
L289 | Workflow setup | Walk mode selection | Partial | Critical | Hard | Route with pedestrian profile. | Browser: Walk visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Walking requires safe paths.
L290 | Workflow setup | Private-vehicle selection | Complete in code | Important | Moderate | Keep chosen mode and route behavior aligned. | Browser: Option visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Defines live routing path.
L291 | Workflow setup | Public-transport selection | Partial | Important | Hard | Carry destination into Travel tab. | Browser: Option visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Transit needs a separate journey.
L292 | Workflow setup | Solo workflow card | Complete in code | Critical | Moderate | Check route and sign-in gates. | Browser: Option visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Primary individual journey.
L293 | Workflow setup | Group Travel workflow card | Partial | Important | Hard | Check real trip and member prerequisites. | Browser: Option visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Group actions need a shared context.
L294 | Workflow setup | Seat Share workflow card | Partial | Important | Hard | Check trip and offer prerequisites. | Browser: Option visible in setup; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Rideshare claims need real capacity.
L295 | Workflow setup | Destination status in setup | Complete in code | Critical | Easy | Reflect selected destination after search. | Browser: No destination set shown initially; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Prevents starting the wrong trip.
L296 | Workflow setup | Set-destination shortcut | Complete in code | Critical | Easy | Focus search from setup. | Browser: Set button visible; Source: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Completes the setup path.
L297 | Workflow setup | Start-Live readiness gate | Partial | Critical | Hard | Check loading, missing route and ready cases. | Code only: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Do not start without a valid route.
L298 | Workflow setup | Inline sign-in prompt | Partial | Critical | Hard | Reconcile setup and directions auth behavior. | Browser: Sign in to start shown in setup; Source: InlineSignInModal.tsx | See acceptance / next action | UI extension | Current entry paths gave mixed signals.
L299 | Workflow setup | Online/offline helper card | Partial | Critical | Moderate | Show actual network state. | Code only: LiveEmptyStateCard.tsx | See acceptance / next action | UI extension | Avoids trusting stale results.
L300 | Workflow setup | Group meet-point prompt | Partial | Important | Moderate | Set and verify shared meeting point. | Code only: LiveSetupPanel.tsx | See acceptance / next action | UI extension | Group members need one agreed target.
L301 | Accessibility and feedback | Search accessible label | Partial | Critical | Easy | Give field a spoken name. | Browser: AX exposed unnamed text field; Source: LivePageClient.tsx | See acceptance / next action | UI extension | Current AX field had no name.
L302 | Accessibility and feedback | Dock stage spoken labels | Complete in code | Important | Easy | Check every tool's label. | Browser: AX exposed named tool checkboxes; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Icon-only rail needs names.
L303 | Accessibility and feedback | Unavailable stage explanation | Partial | Important | Moderate | Use stage-specific prerequisite copy. | Browser: Multiple prerequisites ended with generic future-phase copy; Source: LiveDockRail.tsx | See acceptance / next action | UI extension | Generic future-phase toast obscures real state.
L304 | Accessibility and feedback | Place tabs keyboard navigation | Partial | Critical | Moderate | Test arrows and tab order. | Code only: PlacePanelLiveChrome.tsx | See acceptance / next action | UI extension | Keyboard users need place facts.
L305 | Accessibility and feedback | Report modal focus trap | Partial | Critical | Moderate | Test focus on open/close and Escape. | Code only: LiveReportModal.tsx | See acceptance / next action | UI extension | Prevents inaccessible dialog state.
L306 | Accessibility and feedback | Map controls keyboard activation | Partial | Critical | Hard | Test zoom, compass, layers and locate. | Code only: LiveMapRightControls.tsx | See acceptance / next action | UI extension | Core map actions need keyboard access.
L307 | Accessibility and feedback | Low-vision map control contrast | Partial | Important | Moderate | Check against imagery and all styles. | Code only: LiveMapRightControls.tsx | See acceptance / next action | UI extension | Floating controls must remain visible.
L308 | Accessibility and feedback | Offline status banner | Partial | Critical | Moderate | Disconnect network and inspect recovery. | Code only: LiveEmptyStateCard.tsx | See acceptance / next action | UI extension | Avoids stale data appearing current.
L309 | Accessibility and feedback | Route failure card | Partial | Critical | Moderate | Simulate route provider failure. | Code only: LiveEmptyStateCard.tsx | See acceptance / next action | UI extension | Users need a next step.
L310 | Accessibility and feedback | GPS permission-denied card | Partial | Critical | Moderate | Deny permission and inspect alternatives. | Code only: LiveEmptyStateCard.tsx | See acceptance / next action | UI extension | Manual planning should remain available.
L311 | Accessibility and feedback | Toast dismissal | Complete in code | Important | Easy | Close each notice without losing state. | Code only: LiveMapNoticeStack.tsx | See acceptance / next action | UI extension | Keeps map uncluttered.
L312 | Accessibility and feedback | Persistent action success accuracy | Partial | Critical | Hard | Audit all saved/sent/updated copy against real effects. | Code only: LivePageClient.tsx | See acceptance / next action | UI extension | False success is a product trust defect.

## Review
Live review — decisions and verification
Review date | 2026-09-24 12:00
Context | User requested the same feature, UI and graphical inventory used for Explorer.
Decision | Prioritize truthful search, identity, routing and action outcomes before more map effects.
Priority | Meaning | Recommended action | Evidence / limitation
Critical | Blocks the core journey or risks misleading location, navigation, cost or action outcomes. | Resolve and verify before treating Live as dependable. | Importance is separate from implementation status and difficulty.
Important | Material user value, but can be scoped or deferred without invalidating the core map journey. | Complete after Critical gates; hide unavailable actions clearly. | Includes saves, useful group workflows and map readability.
Later | Optional expansion or visual enhancement. | Defer until the core journey is verified. | Includes satellite variants, globe polish, booking stubs and assistant extras.
Status | Meaning | Verification expectation
Complete in code | Scoped implementation exists; no known missing core behavior found in this review. | Code-only evidence needs runtime verification. | Not an end-to-end, device or production certification.
Partial | A surface or integration exists, but a gap, issue or material unverified dependency remains. | Meet each row acceptance criterion before upgrading. | No production readiness percentage is calculated.
Pending | Unavailable, toast-only, placeholder, or deliberately gated. | Implement only when prioritized and verify persistent behavior. | Dark is deliberately disabled; it is not an accidental defect.
Finding | Impact | Next action | Evidence
Discovery layer unavailable | Default parks/capitals overlay could not be relied on in this browser session. | Investigate actual failure and verify retry/empty states. | Observed layer unavailable · try again.
Navigation progress mismatch | Solo overlay showed 0 m left alongside a 0.1 mi turn distance and 1 min ETA. | Use route progress/provider duration and test moving GPS. | Browser observation; SoloLiveNavigationOverlay.tsx derives ETA from destination distance.
False success feedback | Parking, arrival updates and nudges include toast-only callbacks. | Persist/deliver actions before showing saved/sent/arrived. | LivePageClient.tsx callbacks inspected; no messages sent.
Group entry integration gap | Visible place Put to vote / Invite actions still use coming-soon callbacks. | Connect existing trip-aware poll path to visible controls. | use-live-group-vote.ts exists; liveChrome callbacks remain stubs.
Auth entry inconsistency | Setup says sign in to start; route Start directions entered Solo Live in the same session. | Define and enforce intended guest-versus-authenticated policy. | Observed browser paths; no credentials entered.
Enriched identity consistency | Place title changed to Bakery while the Info category remained Cafe. | Reconcile preview and enriched fields and verify nearest-place matching. | Pan Artesanal sample; mismatch is not proof of a wrong underlying venue.
Search naming / loading | AX search field lacked a name; Searching briefly remained alongside returned results. | Add an accessible name and verify loading-state timing. | Browser AX tree; searching indicator later cleared.
Verified sample | Map rendering; setup; layers menu; 15 category options; 12 coffee results and pins; place tabs; route ready; Solo start/end; report modal. | Treat this as a sampled browser review. | No reports, saves, invitations, seat joins or financial actions submitted.
Not verified | Real GPS movement; desktop/breakpoint matrix; every base/overlay render; authenticated group/seat/expense persistence; production providers. | Run targeted scenarios before upgrading dependent rows. | No new unit/integration test suite run; source inspection is not runtime verification.
Source root | frontend/app/(dashboard)/live/ |  | Relative code references in Live Tasks are under this folder; AIAssistantSidecar.tsx is in frontend/components/ai.
Source URL | http://localhost:3000/live |  | Current browser review target.
Reference format | Scram Book/Explorer Tab/Rovvy_Explorer_Scrum_Book.xlsx |  | Matched status / importance / difficulty separation, filters, dropdowns and color conventions.
Product decisions | Scram Book/Live Tab/README.md; Rovvy_Live_v3_Design_Review.md; Rovvy_Live_Tab_Technical_Documentation.md |  | Historical shipped claims were cross-checked where practical; current source takes precedence.
Result | Completed inventory and criticality review in the Live Scram Book. | Next: navigation truth and action-feedback fixes, then discovery failure investigation. | Documentation only; application code unchanged.
Counting scope | One row per separately assessable control, display, action or behavior. | Do not interpret item counts as engineering effort or production readiness. | Some rows are parts of one journey, but each has a distinct acceptance check.